## 00 Presales Discovery
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Workshop Planning
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Workshop objectives defined
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Participant list confirmed (business stakeholders, SMEs, end users)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Date/time scheduled (minimum 4 hours)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Location/Teams meeting booked
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Pre-read materials sent to participants
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Whiteboard/collaboration tools prepared (Miro, Mural)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Materials Prepared
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Workshop agenda created
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Current state process maps (if available)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Pain points discussion guide
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Use case template ready
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.1 Business Requirements Workshop Preparation | Recording setup arranged
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Workshop Session 1: Current State (2 hours)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Welcome and introductions
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Project context and objectives reviewed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Current business processes mapped
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Pain points identified and prioritized
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Quantitative metrics captured (time, cost, volume, errors)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Stakeholder perspectives documented
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Constraints and limitations identified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Workshop Session 2: Future State (2 hours)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Desired future state envisioned
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Business objectives clarified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Success criteria discussed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | User personas created
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Key scenarios identified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Integration points identified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Non-functional requirements gathered (performance, security, compliance)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Current state process maps
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Pain points list (prioritized)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Business objectives documented
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | User personas
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.2 Business Requirements Workshop Execution | Initial requirements list
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Use Case Identification
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | All potential AI use cases listed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Each use case described (problem, proposed solution, benefit)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Business value assessed for each
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Technical feasibility estimated for each
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Implementation complexity assessed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Dependencies identified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Use Case Prioritization
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Prioritization criteria defined (value, feasibility, effort, risk)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Use cases scored against criteria
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Priority order established
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | MVP use cases selected (typically 2-3)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Future phase use cases parked
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Detailed Use Case Specifications (for MVP)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Use case name and ID
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Business problem description
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Current process description
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Proposed AI solution
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Expected outcomes and benefits
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Success metrics
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | User stories written (As a [user], I want [action] so that [benefit])
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Acceptance criteria defined
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Data requirements identified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Integration requirements specified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Constraints and assumptions documented
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Use case inventory
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Prioritization matrix
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | Detailed use case specifications (MVP)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.3 Use Case Definition | User stories with acceptance criteria
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Functional Requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Core features listed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | User interactions specified
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | System behaviors defined
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Business rules documented
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Workflow sequences captured
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Integration requirements detailed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Non-Functional Requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Performance requirements (response time, throughput)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Scalability requirements (users, data volume, transactions)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Availability requirements (uptime %)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Security requirements (authentication, authorization, encryption)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Compliance requirements (GDPR, HIPAA, industry standards)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Usability requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Accessibility requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Maintainability requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Disaster recovery requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Data Requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Input data requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Output data requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Data formats and schemas
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Data volume estimates
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Data freshness requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Data retention requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Data quality requirements
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Requirements Review
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Business Owner review completed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Technical team review completed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Compliance/Legal review completed
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Feedback incorporated
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Requirements signed off
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Business Requirements Document (BRD)
WEEK 1: BUSINESS REQUIREMENTS & USE CASES | 1.4 Requirements Documentation | Requirements sign-off
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data Inventory
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | All potential data sources identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data source owners identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data locations documented (databases, files, APIs, cloud)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data formats noted (structured, semi-structured, unstructured)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data access methods documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Refresh frequency understood
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data Access Requests
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data access requests submitted
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data sharing agreements reviewed
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | NDA requirements checked
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Access permissions requested
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Sample data requested (anonymized if needed)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data dictionary requested
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data source inventory
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.1 Data Source Identification | Data access status tracker
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data Access Obtained
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Read access to production data (or copies)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Sample datasets received
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data dictionaries/schemas obtained
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data access credentials configured
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data exploration environment set up
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Initial Data Exploration
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data loaded into exploration environment
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Column/field names reviewed
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data types verified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Sample records examined
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data relationships understood
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data lineage documented (where data comes from)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Business logic in data identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Data access confirmed
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.2 Data Access & Exploration | Initial data exploration notes
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Completeness Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Missing value analysis per column
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Null/empty value counts
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Required vs optional fields identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data coverage by time period
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data completeness score calculated
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Completeness issues documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Accuracy Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data validation rules tested
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Range checks performed (min/max, expected ranges)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Format validation (dates, emails, phone numbers)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Cross-field consistency checks
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Duplicate records identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data accuracy score calculated
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Accuracy issues documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Consistency Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data format consistency checked
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Naming convention consistency
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Code/category consistency
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Cross-system consistency (if multiple sources)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Historical consistency
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Consistency issues documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Timeliness Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data freshness assessed
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Update frequency verified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Lag/latency measured
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Historical data availability checked
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Timeliness issues documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Validity Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data conforms to business rules
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Referential integrity checked
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Lookup values validated
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data type appropriateness
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Validity issues documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Uniqueness Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Duplicate detection
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Primary key validation
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Uniqueness violations identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Uniqueness issues documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data quality assessment report
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data quality scores by dimension
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data quality issues log
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.3 Data Quality Assessment | Data quality improvement recommendations
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Volume Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Total record counts
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Growth trends analyzed
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Data volume by category/class
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Historical data availability (years/months)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Projected future volumes
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Distribution Analysis
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Feature distributions plotted
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Class balance analyzed (for classification)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Outlier detection
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Skewness identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Statistical summaries created (mean, median, std dev)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Sufficiency Assessment
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Minimum data requirements for ML defined
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Current data compared to minimum
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Data gaps identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Sufficiency by use case assessed
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Data augmentation needs identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Data volume report
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Distribution analysis charts
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.4 Data Volume & Distribution Analysis | Data sufficiency assessment
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Data Classification
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Personal data (PII) identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Sensitive data identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Confidential data identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Public data identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Data classification labels applied
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Privacy Requirements
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | GDPR applicability assessed (if EU data)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | CCPA applicability assessed (if CA data)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Industry-specific regulations identified (HIPAA, FERPA, etc.)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Data residency requirements identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Consent requirements understood
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Right to deletion requirements
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Privacy Impact Assessment
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | DPIA (Data Privacy Impact Assessment) initiated
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Privacy risks identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Privacy controls designed
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Anonymization/pseudonymization needs determined
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Data masking requirements identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Compliance Review
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Legal/Compliance team consulted
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Regulatory requirements documented
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Compliance gaps identified
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Remediation plans created
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Compliance sign-off obtained (or conditions noted)
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Data classification register
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Privacy Impact Assessment
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Compliance requirements document
WEEK 2: DATA DISCOVERY & ASSESSMENT | 2.5 Data Privacy & Compliance Assessment | Privacy/compliance sign-off
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | ML Problem Type Identification
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Problem framed as ML problem type:
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Classification (binary, multi-class, multi-label)
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Regression
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Clustering
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Forecasting/Time Series
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Anomaly Detection
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | NLP (sentiment, NER, summarization, etc.)
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Computer Vision (object detection, classification, etc.)
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Recommendation
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Reinforcement Learning
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Problem complexity assessed
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Success metrics defined (accuracy, precision, recall, F1, RMSE, etc.)
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Input/Output Definition
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Model inputs (features) identified
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Model outputs (predictions) defined
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Feature engineering opportunities identified
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Output format specified
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Baseline Definition
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Current baseline approach documented (rules-based, manual, etc.)
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Baseline performance measured
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Minimum acceptable improvement over baseline defined
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | ML problem definition document
WEEK 3: AI/ML APPROACH DESIGN | 3.1 Problem Framing | Baseline performance metrics
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Algorithm Candidates Identified
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Traditional ML algorithms considered:
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Decision Trees / Random Forests
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Gradient Boosting (XGBoost, LightGBM)
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Linear/Logistic Regression
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | SVM
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | K-Nearest Neighbors
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Deep Learning approaches considered:
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Neural Networks
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | CNNs (for images)
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | RNNs/LSTMs (for sequences)
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Transformers (for NLP)
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Pre-trained models / Transfer Learning:
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure Cognitive Services
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure OpenAI
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Hugging Face models
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Custom pre-trained models
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Approach Comparison
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Each approach evaluated on:
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Trade-offs documented
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Recommendation made
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure Services Selection
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure services identified:
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure Machine Learning
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure Cognitive Services
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure OpenAI Service
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure Databricks
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Custom approach
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Service pros/cons assessed
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Cost estimates for each
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Recommendation made
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Algorithm evaluation matrix
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Recommended ML approach
WEEK 3: AI/ML APPROACH DESIGN | 3.2 ML Approach Selection | Azure services selection
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature Identification
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Raw features from data sources listed
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Derived features identified
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Engineered features planned:
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Aggregations (sum, avg, count, etc.)
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Ratios and proportions
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Date/time features (day of week, hour, season)
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Text features (length, word count, TF-IDF)
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Categorical encodings (one-hot, label, target)
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Interaction features
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Domain-specific features
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature Selection Plan
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature importance analysis planned
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Dimensionality reduction considered (PCA, etc.)
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature selection criteria defined
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature Store Strategy
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Need for feature store assessed
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature store approach defined (if needed)
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature versioning strategy
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature engineering plan
WEEK 3: AI/ML APPROACH DESIGN | 3.3 Feature Engineering Strategy | Feature list (raw + engineered)
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Training Approach
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Training/validation/test split strategy (e.g., 70/15/15)
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Cross-validation strategy (k-fold, time-based)
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Hyperparameter tuning approach
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Model ensembling strategy (if applicable)
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Training Infrastructure
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Compute requirements estimated
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Azure ML compute clusters sized
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Training time estimated
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Training cost estimated
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Experiment Tracking
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Experiment tracking approach defined (Azure ML, MLflow)
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Metrics to track identified
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Model versioning strategy
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Model training plan
WEEK 3: AI/ML APPROACH DESIGN | 3.4 Model Training Strategy | Compute requirements document
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Evaluation Metrics
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Primary metric defined
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Secondary metrics defined
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Business metrics mapped to technical metrics
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Minimum acceptable thresholds set
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Evaluation Approach
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Hold-out test set approach
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Cross-validation approach
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Temporal validation (for time series)
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | A/B testing strategy (for production)
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Fairness & Bias Assessment
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Protected attributes identified
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Fairness metrics defined
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Bias detection approach planned
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Mitigation strategies identified
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Interpretability Requirements
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Interpretability needs assessed
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Explainability techniques identified (SHAP, LIME, etc.)
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Model transparency requirements
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Model evaluation plan
WEEK 3: AI/ML APPROACH DESIGN | 3.5 Model Evaluation Strategy | Success criteria document
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Architecture Components
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Data ingestion layer designed
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Data processing/transformation layer
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Feature engineering layer
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Model training layer
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Model serving/inference layer
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Application layer
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Integration layer
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Monitoring layer
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Azure Services Mapping
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Each component mapped to Azure services
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Service tiers selected
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Redundancy/HA approach defined
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Disaster recovery approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Architecture Diagram
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | High-level architecture diagram created
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Data flow diagram created
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Component relationships shown
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | External systems shown
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Solution architecture document
WEEK 3-4: SOLUTION ARCHITECTURE | 4.1 High-Level Architecture Design | Architecture diagrams
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data Pipeline Design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data sources and ingestion methods
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data transformation logic
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data validation rules
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data quality checks
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Error handling approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data pipeline orchestration (Azure Data Factory, Synapse)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data Storage Design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Raw data storage (Data Lake)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Processed data storage
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Feature store (if applicable)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Model artifacts storage
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Metadata storage
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data retention policies
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data archival strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data Governance
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data lineage tracking
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data cataloging (Azure Purview)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data access controls
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data encryption (at rest, in transit)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data masking/anonymization
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data architecture document
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data pipeline design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.2 Data Architecture | Data governance plan
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Training Architecture
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Training pipeline design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Experiment tracking setup
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Hyperparameter tuning approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Distributed training (if needed)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Model registration process
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Serving Architecture
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Inference approach (real-time, batch, streaming)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Model deployment approach (AKS, ACI, Azure Functions)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Scaling strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Model versioning strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | A/B testing setup (if needed)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Model rollback strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | MLOps Architecture
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | CI/CD pipeline design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Automated testing strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Model retraining triggers
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Model monitoring approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | Alert configuration
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | ML architecture document
WEEK 3-4: SOLUTION ARCHITECTURE | 4.3 ML Architecture | MLOps design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Application Architecture
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | User interface design approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Backend services design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | API design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Authentication/authorization approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Session management
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Integration Architecture
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Integration patterns defined (REST API, messaging, events)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | External system integrations designed
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | API specifications
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Data synchronization approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Error handling and retries
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Deployment Architecture
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Environment strategy (dev, test, prod)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Infrastructure as Code approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Deployment automation
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Blue-green or canary deployment
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Application architecture document
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | Integration specifications
WEEK 3-4: SOLUTION ARCHITECTURE | 4.4 Application & Integration Architecture | API documentation
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Security Requirements
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Authentication requirements (Azure AD, OAuth)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Authorization requirements (RBAC)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Encryption requirements
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Network security requirements
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | API security requirements
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Security Controls
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Identity and access management design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Network security design (NSGs, firewalls)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Encryption design (at rest, in transit)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Key management (Azure Key Vault)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Threat protection (Defender for Cloud)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Security monitoring and logging
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Compliance Controls
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Compliance requirements mapped to controls
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Audit logging design
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Compliance reporting approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Security architecture document
WEEK 3-4: SOLUTION ARCHITECTURE | 4.5 Security Architecture | Security controls matrix
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Monitoring Strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Application monitoring (Application Insights)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Infrastructure monitoring (Azure Monitor)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Model performance monitoring
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Data quality monitoring
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Business metrics monitoring
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Alerting Strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Alert definitions
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Alert thresholds
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Alert routing
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Escalation procedures
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Logging Strategy
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Log aggregation (Log Analytics)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Log retention policies
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Log analysis approach
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Dashboards
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Dashboard requirements
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Dashboard design (Power BI, Azure Dashboard)
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Dashboard audiences
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Monitoring and observability plan
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Alert definitions
WEEK 3-4: SOLUTION ARCHITECTURE | 4.6 Monitoring & Observability | Dashboard designs
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Proof of Concept (Optional but Recommended)
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | POC objectives defined
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Sample data prepared
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Quick model built
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Baseline performance achieved
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Technical risks validated/mitigated
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | POC results documented
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Feasibility Assessment
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Data sufficiency confirmed
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Model accuracy achievable
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Performance requirements achievable
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Integration complexity manageable
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Cost reasonable
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Timeline realistic
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Risk Assessment
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Technical risks updated
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Data risks updated
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Mitigation plans updated
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | No blocking risks
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | POC results (if conducted)
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Feasibility assessment report
WEEK 4: VALIDATION & PLANNING | 5.1 Technical Feasibility Validation | Updated risk register
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Internal Review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Technical team review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Architecture review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Security review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Data team review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Feedback incorporated
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Stakeholder Review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Business Owner review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Executive Sponsor briefing
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | CIO/CTO review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Compliance/Legal review
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Feedback incorporated
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Design Sign-off
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Business requirements approved
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Solution architecture approved
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Data architecture approved
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Security architecture approved
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | ML approach approved
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Review feedback log
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Updated architecture documents
WEEK 4: VALIDATION & PLANNING | 5.2 Solution Design Review | Design sign-offs
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Prototype Scope Definition
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | MVP features identified
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Out of scope clarified
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Prototype success criteria defined
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Demo scenarios planned
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Prototype Sprint Planning
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Number of sprints determined (typically 3-4)
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Sprint goals defined
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Sprint backlog created
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Story pointing completed
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Team velocity estimated
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Resource Planning
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Team members confirmed
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Allocation percentages confirmed
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Any skill gaps identified
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Training needs identified
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Environment Planning
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Prototype environment requirements
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Azure resource provisioning plan
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Tool setup requirements
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Prototype scope document
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Sprint plan
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Resource plan
WEEK 4: VALIDATION & PLANNING | 5.3 Prototype Phase Planning | Environment plan
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Discovery Report
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Executive summary
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Business requirements summary
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Use cases documented
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Data assessment summary
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Solution architecture summary
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | ML approach summary
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Feasibility conclusion
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Risks and mitigation
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Recommendation (proceed/adjust/stop)
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Supporting Documentation
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Business Requirements Document
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Data Assessment Report
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Solution Architecture Document
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | ML Approach Document
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Risk Register (updated)
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Prototype Plan
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Artifacts
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Architecture diagrams
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Data flow diagrams
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | ER diagrams
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Wireframes/mockups (if created)
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | POC code/models (if created)
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | Discovery Report
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | All supporting documents
WEEK 4: VALIDATION & PLANNING | 5.4 Discovery Documentation | All artifacts
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Readiness Assessment
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | All deliverables complete
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | All reviews and sign-offs obtained
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | No blocking issues
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Team ready for prototype
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Phase Gate Presentation
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Executive summary slide
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Business requirements summary
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Data assessment results
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Solution architecture overview
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | ML approach
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Feasibility conclusion
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Risks and mitigation
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Prototype plan
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Budget and timeline
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Go/No-Go recommendation
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Phase Gate Meeting Scheduled
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Date: ___________
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Attendees confirmed (Steering Committee)
DISCOVERY PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Materials distributed in advance
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | Business requirements documented and approved
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | Data assessment complete
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | AI/ML approach defined
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | Solution architecture approved
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | Technical feasibility confirmed
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | Prototype plan created
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | Risks assessed and manageable
DISCOVERY PHASE GATE REVIEW | 6.2 Exit Criteria Assessment | Stakeholder alignment
DISCOVERY PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Decision: GO / CONDITIONAL GO / NO-GO
DISCOVERY PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Conditions (if any): ___________
DISCOVERY PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Decision maker: ___________
DISCOVERY PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Date: ___________
DISCOVERY PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Communicated to stakeholders
Transition to Prototype |  | Prototype Kickoff Scheduled
Transition to Prototype |  | Prototype Sprint 1 Planned
Transition to Prototype |  | Discovery Lessons Learned
Transition to Prototype |  | Discovery Phase Closed