## 01 Mobilisation
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
PHASE GATE: Project Approved to Start |  | Initial Project Concept Approved
PHASE GATE: Project Approved to Start |  | Preliminary Budget Allocated
PHASE GATE: Project Approved to Start |  | Executive Sponsor Identified
PHASE GATE: Project Approved to Start |  | Project Manager Assigned
1. PROJECT FOUNDATION (Week 1) | 1.1 Project Initiation | Project Manager assigned and onboarded
1. PROJECT FOUNDATION (Week 1) | 1.1 Project Initiation | Initial project folder structure created
1. PROJECT FOUNDATION (Week 1) | 1.1 Project Initiation | Project repository setup
1. PROJECT FOUNDATION (Week 1) | 1.1 Project Initiation | Project kick-off meeting scheduled
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Core team roles identified
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Executive Sponsor: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Business Owner: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Project Manager: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | AI/ML Lead: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Data Scientist(s): ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Solution Architect: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Data Engineer: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | DevOps/MLOps Engineer: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Business Analyst: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Change Manager: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Security Manager: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Extended team identified
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Software Engineers: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | QA Lead: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | UX Designer: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Technical Operations: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Compliance/Legal: ___________
1. PROJECT FOUNDATION (Week 1) | 1.2 Team Identification | Resource allocation confirmed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.1 Project Charter | Project Charter drafted
2. GOVERNANCE & PLANNING (Week 1-2) | 2.1 Project Charter | Stakeholder section complete
2. GOVERNANCE & PLANNING (Week 1-2) | 2.1 Project Charter | Project Charter reviewed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.1 Project Charter | Project Charter approved
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Business Case development started
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Benefits analysis completed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Cost analysis completed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Financial analysis completed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Risk assessment for business case
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Alternatives documented
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Business Case reviewed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.2 Business Case | Business Case approved
2. GOVERNANCE & PLANNING (Week 1-2) | 2.3 RACI Matrix | All project roles identified
2. GOVERNANCE & PLANNING (Week 1-2) | 2.3 RACI Matrix | All key activities/decisions listed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.3 RACI Matrix | RACI assignments made for each activity
2. GOVERNANCE & PLANNING (Week 1-2) | 2.3 RACI Matrix | RACI Matrix reviewed with team
2. GOVERNANCE & PLANNING (Week 1-2) | 2.3 RACI Matrix | Conflicts resolved
2. GOVERNANCE & PLANNING (Week 1-2) | 2.3 RACI Matrix | RACI Matrix approved
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | High-level project phases defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Mobilisation: [Start] - [End]
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Discovery: [Start] - [End]
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Prototype: [Start] - [End]
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Build: [Start] - [End]
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Test & Evaluate: [Start] - [End]
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Deploy & Scale: [Start] - [End]
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Operate & Care: [Start] - Ongoing
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Key milestones identified
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Detailed mobilisation plan created
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Sprint structure defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Resource plan created
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Project timeline reviewed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.4 Project Plan & Roadmap | Project Plan approved
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Risk register template created
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Initial risks identified
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Technical risks (min. 3)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Data risks (min. 2)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Business risks (min. 3)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Organizational risks (min. 2)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Project management risks (min. 2)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | For each risk, documented:
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Top 5 risks reviewed with leadership
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Mitigation actions assigned
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Risk review meetings scheduled (weekly)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.5 Risk Register | Risk escalation process defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Stakeholder analysis completed
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Communication matrix created
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Communication channels setup
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Microsoft Teams channel created
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | SharePoint site created and configured
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Email distribution lists created
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Dashboard tool selected (Power BI)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Project management tool configured
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Meeting cadences established
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Daily standups scheduled
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Weekly team meetings scheduled
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Bi-weekly sprint reviews scheduled
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Bi-weekly sprint retrospectives scheduled
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Bi-weekly business reviews scheduled
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Monthly steering committee scheduled
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | Communication templates created
2. GOVERNANCE & PLANNING (Week 1-2) | 2.6 Communication Plan | First status report scheduled
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Business KPIs defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Primary business outcome KPI
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Cost reduction KPI (if applicable)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Revenue impact KPI (if applicable)
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Customer satisfaction KPI
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Productivity KPI
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | For each business KPI:
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Technical KPIs defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Model accuracy target
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Model precision target
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Model recall target
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | System uptime target
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Response time target
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Data quality targets
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | User adoption KPIs defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Project delivery KPIs defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Phase gate success criteria defined
2. GOVERNANCE & PLANNING (Week 1-2) | 2.7 Success Criteria & KPIs | Success criteria reviewed and approved
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Complete stakeholder register created
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Detailed stakeholder analysis completed
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Executive Sponsor analysis
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Business Owner analysis
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | End Users analysis
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | CIO/CTO analysis
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | CFO analysis
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | IT Operations analysis
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Compliance/Legal analysis
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | For each key stakeholder:
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Power/Interest matrix created
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Champions program designed
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Initial stakeholder outreach completed
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Executive Sponsor briefed
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Business Owner engaged
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | CIO/CTO informed
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | CFO briefed
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | IT Operations contacted
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.1 Stakeholder Management | Compliance/Legal engaged
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.2 Project Kickoff | Kickoff meeting prepared
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.2 Project Kickoff | Kickoff meeting content includes:
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.2 Project Kickoff | Kickoff meeting held
3. STAKEHOLDER ENGAGEMENT (Week 1-2) | 3.2 Project Kickoff | Kickoff meeting follow-up
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Azure subscription setup
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Subscription created/assigned
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Subscription naming convention applied
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Cost management configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Budgets and alerts set
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Resource organization
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Management groups configured (if applicable)
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Resource groups created (dev, test, prod)
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Naming conventions defined and documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Tagging strategy defined
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Identity and access management
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Azure AD groups created for project team
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Role-based access control (RBAC) configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Service principals created for automation
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Managed identities configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Networking
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Virtual networks created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Subnets configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Network security groups defined
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Private endpoints configured (if required)
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Development environment setup
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Azure Machine Learning workspace created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Storage accounts created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Key Vault created for secrets
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Application Insights for monitoring
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | DevOps foundations
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Azure DevOps project created OR GitHub repo created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Build pipelines initialized
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Release pipelines planned
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Branch strategy defined (e.g., GitFlow)
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Security baseline
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Azure Security Center enabled
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Microsoft Defender for Cloud configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Security policies applied
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Compliance standards configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Monitoring and logging
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Log Analytics workspace created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Diagnostic settings configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Alerts configured for critical resources
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Dashboard created for environment health
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Documentation
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Environment architecture documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Access procedures documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Naming conventions documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.1 Azure Environment Setup | Environment inventory created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Development tools configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | VS Code / Visual Studio setup guide created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Required extensions identified
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Python environment setup documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Required libraries/packages identified
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Code standards defined
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Coding standards documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Code review process defined
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Linting rules configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Code formatting rules set (e.g., black, flake8)
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Version control setup
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Repository structure created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | .gitignore configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | README.md created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Contributing guidelines documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | CI/CD framework
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | CI pipeline template created
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | CD pipeline strategy defined
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Testing strategy in pipeline defined
4. TECHNICAL FOUNDATION (Week 1-3) | 4.2 Development Tools & Standards | Approval gates configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data sources identified
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Source systems documented
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data owners identified
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data access requests submitted
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data platform components
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Azure Data Lake or Blob Storage configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Azure Data Factory created (if needed)
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Azure Synapse or Databricks configured (if needed)
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data ingestion framework designed
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data governance
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data classification completed
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data retention policies defined
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data access controls configured
4. TECHNICAL FOUNDATION (Week 1-3) | 4.3 Data Platform Setup (If Applicable) | Data lineage strategy defined
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Security assessment initiated
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Security requirements documented
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Compliance requirements identified (GDPR, HIPAA, etc.)
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Threat model created
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Security controls identified
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Privacy assessment
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Data Privacy Impact Assessment (DPIA) initiated
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Personal data identified
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Data processing activities documented
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Privacy controls defined
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Consent mechanisms designed (if required)
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Compliance checkpoints
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Regulatory requirements reviewed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Industry standards identified
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Compliance framework selected
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Audit requirements defined
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.1 Security & Compliance | Security reviews scheduled
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Contracts reviewed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | SOW (Statement of Work) signed (if external partner)
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | MSA (Master Services Agreement) in place
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | NDAs signed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Data sharing agreements reviewed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Intellectual property
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | IP ownership clarified
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Code ownership documented
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Model ownership documented
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Open source licenses reviewed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Liability and insurance
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Liability coverage reviewed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Insurance requirements met
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.2 Legal & Contractual | Risk transfer mechanisms in place
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Change impact assessment initiated
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Affected user groups identified
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Impact on current processes documented
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Change readiness assessed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Change management strategy defined
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Communication approach determined
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Training approach planned
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Champions program designed
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Resistance management plan created
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Training planning started
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Training needs analysis initiated
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Training delivery methods determined
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Training materials development planned
5. GOVERNANCE & COMPLIANCE (Week 2-3) | 5.3 Change Management Planning | Trainer identification started
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Detailed budget created
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Personnel costs detailed
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Azure infrastructure costs estimated
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Software licenses costed
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | External services/consultants budgeted
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Training and change management budgeted
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Contingency (15%) added
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Budget tracking setup
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Budget tracking spreadsheet/tool configured
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Cost center/charge codes obtained
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Azure cost management configured
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Spending alerts set
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Monthly budget review scheduled
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Procurement initiated
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Software licenses identified and requested
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | External consultants contracted (if needed)
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Training vendors identified (if needed)
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Financial governance
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Approval thresholds defined
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Purchase order process understood
6. BUDGET & FINANCIALS (Week 2-3) | 6.1 Budget Management | Expense reporting process established
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Onboarding materials created
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Project overview deck
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Technical architecture overview
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Access procedures documented
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Team contact list
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Tool usage guides
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Team onboarding sessions held
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Project overview session: ___________
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Technical deep dive: ___________
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Tool training: ___________
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Process training: ___________
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Individual team member onboarding
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | All core team members onboarded
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Azure access granted
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | DevOps/GitHub access granted
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | SharePoint access granted
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.1 Team Onboarding | Teams channel access granted
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Team AI/ML skills assessed
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Current skill levels documented
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Skill gaps identified
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Training needs determined
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Training plan created (if needed)
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Azure ML training identified
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Python/data science training identified
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | MLOps training identified
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Training scheduled
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | External expertise engaged (if needed)
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Microsoft partners/consultants identified
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Engagement model defined
7. KNOWLEDGE TRANSFER & TRAINING (Week 2-3) | 7.2 AI/ML Capability Assessment | Knowledge transfer plan created
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Discovery phase planned
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Discovery objectives defined
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Discovery activities listed
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Discovery timeline created
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Discovery team identified
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Requirements gathering approach
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Workshop format defined
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Participant list created
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Workshop materials prepared
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Facilitator assigned
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Data discovery planning
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Data sources to assess identified
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Data access requests submitted
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Data quality assessment plan created
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | Data assessment tools identified
8. INITIAL DISCOVERY PREP (Week 3) | 8.1 Discovery Planning | First discovery workshop scheduled
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Quality standards defined
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Code quality standards
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Documentation standards
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Testing standards
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Model quality standards
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Quality assurance roles
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | QA lead identified: ___________
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Quality gates defined
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Review processes established
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Quality metrics
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Defect tracking process defined
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Quality KPIs identified
9. QUALITY ASSURANCE (Week 3) | 9.1 Quality Framework | Quality dashboard planned
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | All deliverables complete
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Project Charter ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Business Case ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | RACI Matrix ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Project Plan & Roadmap ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Risk Register ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Communication Plan ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Success Criteria & KPIs ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Stakeholder Analysis ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Azure Environment (Dev) ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Team Onboarded ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | All approvals obtained
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Project Charter approved ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Business Case approved ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Budget approved ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Executive Sponsor committed ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Team ready
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | All core roles filled ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Team onboarded and trained ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Tools and access provided ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Foundation established
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Governance in place ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Communication channels active ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Risk management operational ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.1 Mobilisation Completeness Check | Technical environment ready ✓
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.2 Mobilisation Phase Gate Review | Phase gate review meeting scheduled
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.2 Mobilisation Phase Gate Review | Phase gate presentation prepared
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.2 Mobilisation Phase Gate Review | Phase gate review held
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.2 Mobilisation Phase Gate Review | Go/No-Go decision documented
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.3 Transition to Discovery | Discovery phase kickoff scheduled
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.3 Transition to Discovery | Discovery workshop scheduled
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.3 Transition to Discovery | Mobilisation lessons learned captured
10. MOBILISATION REVIEW & GATE (Week 3-4) | 10.3 Transition to Discovery | Mobilisation phase closed