## 02 Hackathons
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Kickoff Session with ALL Stakeholders
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Date: ___________
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Business stakeholders committed (end users, business owners, executives)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Technical teams committed (architects, engineers, security, operations)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Microsoft teams invited for Day 3 demo (ATU, STU, FDE, ISD, CSU)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | 3-Day Hackathon Approach Explained
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Hackathon goal: Prove or disprove the solution works in 3 days
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Discovery findings will be tested with real code and data
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Business requirements will be validated with working prototype
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Architecture assumptions will be proven or challenged
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Day 3 demo is MANDATORY for all stakeholders
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Day 3 Demo Schedule Locked
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Day 3 demo date/time: ___________
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Calendar holds sent to all stakeholders (non-negotiable)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Demo location/Teams link confirmed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Stakeholder attendance confirmed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Kickoff presentation delivered
PRE-HACKATHON PREPARATION (1 Week Before) | 0.1 Pre-Hackathon Kickoff Meeting (1 Week Before) | Stakeholders committed to active participation
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Day 1 Tasks Identified
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Data pipeline tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Baseline model training tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Infrastructure setup tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Team roles assigned for Day 1
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Day 2 Tasks Identified
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Model optimization tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | API development tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | UI setup tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Team roles assigned for Day 2
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Day 3 Tasks Identified
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Integration tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Demo preparation tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Testing tasks listed
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Team roles assigned for Day 3
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Success Criteria Defined
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Day 1 success criteria clear
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Day 2 success criteria clear
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Day 3 success criteria clear
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Overall hackathon success criteria documented
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | 3-day task plan documented
PRE-HACKATHON PREPARATION (1 Week Before) | 0.2 3-Day Task Breakdown | Team knows what to build each day
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Development Environment
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Azure ML workspace configured
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Compute clusters provisioned
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Dev/Test environments ready
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Data access verified
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Sample datasets loaded
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | DevOps Setup
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Git repository created
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Branch strategy defined (main, develop, feature branches)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | CI/CD pipelines configured (basic)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Code review process established
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Collaboration Tools
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Azure DevOps Boards configured
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Teams channel active
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Documentation location (Wiki, SharePoint)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Daily standup time scheduled
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Monitoring Setup
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Application Insights configured
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Basic logging enabled
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Dashboard created (sprint burndown, velocity)
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Environment ready
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Tools configured
PRE-HACKATHON PREPARATION (1 Week Before) | 0.3 Environment & Tools Setup | Team has access
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Sprint Planning Meeting
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Sprint goal defined
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Sprint backlog selected from product backlog
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Stories assigned to team members
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Definition of Done reviewed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Sprint capacity confirmed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Sprint Commitment
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Team commits to sprint backlog
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Risks identified
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Dependencies confirmed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Sprint 1 backlog finalized
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.1 Sprint Planning (Day 1) | Sprint goal visible
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data Ingestion
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data sources connected
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data extraction scripts/pipelines
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Raw data landed in Data Lake
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Incremental load strategy (if applicable)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data Transformation
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data cleansing logic implemented
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Missing value handling
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Outlier treatment
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data type conversions
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data validation rules
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Feature Engineering
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Raw features extracted
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Derived features created
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Categorical encoding (one-hot, label, target)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Numerical scaling/normalization
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Feature selection applied
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data Pipeline Orchestration
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Azure Data Factory pipeline created (or Synapse, Databricks)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Pipeline scheduling configured
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Error handling implemented
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data quality checks automated
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data Versioning
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Training datasets versioned
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data lineage tracked
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Dataset registered in Azure ML
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Working data pipeline
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Feature-engineered training data
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.2 Data Pipeline Development | Data pipeline code in Git
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model Experimentation
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Experiment tracking set up (MLflow, Azure ML Experiments)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Train/validation/test split created
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Baseline algorithm selected
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Initial model trained
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model Evaluation
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Evaluation metrics calculated (accuracy, precision, recall, F1, RMSE, etc.)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Confusion matrix generated (for classification)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Performance vs. baseline compared
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Results documented
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model Registration
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model saved and versioned
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model registered in Azure ML
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model metadata captured (metrics, parameters, data version)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Baseline model trained
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model performance report
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.3 Baseline Model Development | Model registered
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.4 Daily Standups (Every Day) | Daily Standup Ritual
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.4 Daily Standups (Every Day) | 15-minute timeboxed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.4 Daily Standups (Every Day) | Each team member answers:
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.4 Daily Standups (Every Day) | Blockers escalated immediately
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.4 Daily Standups (Every Day) | Follow-up conversations offline
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.4 Daily Standups (Every Day) | Team synchronized daily
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.4 Daily Standups (Every Day) | Blockers identified and addressed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Demo Preparation
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Demo script prepared
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Demo environment ready
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Real business data loaded
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Backup plan in case of issues
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | PRESSURE TEST Session
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Business stakeholders present and engaged
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Technical teams present (architects, engineers, security)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Microsoft teams participating
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Sprint goal reviewed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Live demonstration:
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Pressure Testing Questions Answered
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | "Does this solve our business problem?" (Business test)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | "Is the data quality sufficient?" (Data test)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | "Will this architecture scale?" (Technical test)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | "Can we integrate this?" (Integration test)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | "Is this secure/compliant?" (Security test)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Immediate Feedback & Pivots
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Feedback captured in real-time
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Critical issues flagged
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Priorities adjusted for next sprint
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Pivot decisions made if needed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Sprint 1 demo completed
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Pressure test findings documented
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.5 Sprint 1 PRESSURE TEST Demo (End of Week 2) | Backlog reprioritized based on feedback
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Retrospective Meeting
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Team only (safe space)
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | What went well?
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | What didn't go well?
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | What will we improve?
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Action Items
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Improvement actions identified
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Owners assigned
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Actions tracked
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Retrospective notes
SPRINT 1: DATA PIPELINE & BASELINE MODEL (Weeks 1-2) | 1.6 Sprint Retrospective (End of Week 2) | Action items for next sprint
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.1 Sprint Planning (Day 1 of Sprint 2) | Sprint Planning Meeting
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.1 Sprint Planning (Day 1 of Sprint 2) | Sprint 1 velocity reviewed
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.1 Sprint Planning (Day 1 of Sprint 2) | Sprint 2 goal defined
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.1 Sprint Planning (Day 1 of Sprint 2) | Sprint 2 backlog selected
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.1 Sprint Planning (Day 1 of Sprint 2) | Stories assigned
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.1 Sprint Planning (Day 1 of Sprint 2) | Sprint 2 backlog finalized
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Hyperparameter Tuning
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Search space defined
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Tuning strategy selected (grid search, random search, Bayesian)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Hyperparameter tuning executed
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Best parameters identified
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Advanced Algorithms
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Alternative algorithms tested (ensemble methods, deep learning, etc.)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Model comparison performed
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Best model selected
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Feature Optimization
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Feature importance analysis
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Feature selection refinement
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | New features experimented
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Feature engineering improved
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Model Validation
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Cross-validation performed
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Model performance on test set
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Overfitting/underfitting checked
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Model meets success criteria
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Optimized model
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Model performance improved over baseline
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.2 Model Improvement | Model comparison report
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.3 Model Explainability | Explainability Implementation
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.3 Model Explainability | SHAP values calculated (or LIME)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.3 Model Explainability | Feature importance visualization
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.3 Model Explainability | Prediction explanations generated
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.3 Model Explainability | Explainability tested with stakeholders
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.3 Model Explainability | Model explainability features
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.3 Model Explainability | Explanation visualizations
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API Design
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API endpoints defined (predict, explain, health)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | Request/response schemas defined
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API documentation (Swagger/OpenAPI)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API Implementation
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | Model loaded in API service
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | Prediction endpoint implemented
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | Input validation implemented
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | Error handling implemented
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | Logging implemented
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API Deployment
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API deployed to Azure (ACI, AKS, or Functions)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API tested (Postman, curl)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API performance validated (latency <100ms target)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | Working prediction API
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API documentation
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.4 Prediction API Development | API deployed to dev environment
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.5 Daily Standups (Every Day) | Daily standups held
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.5 Daily Standups (Every Day) | Progress tracked
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.5 Daily Standups (Every Day) | Blockers resolved
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | PRESSURE TEST Session
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Live demonstration with stakeholders
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Model improvement shown (vs. baseline and business target)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Live API predictions with real business scenarios
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Explainability tested with business users ("Can you explain why?")
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Pressure Testing Questions Answered
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | "Is the accuracy good enough?" (Business value test)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | "Can business users understand the predictions?" (Usability test)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | "Will this integrate with our systems?" (Integration test)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | "Is the API fast enough?" (Performance test)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | "Can we trust the AI?" (Explainability test)
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Immediate Course Corrections
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Model improvements prioritized
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | UI/UX feedback incorporated
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Integration blockers identified and addressed
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Sprint 2 demo completed
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Pressure test results documented
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.6 Sprint 2 PRESSURE TEST Demo (End of Week 4) | Next sprint adjusted based on feedback
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.7 Sprint Retrospective | Retrospective held
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.7 Sprint Retrospective | Improvements identified
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.7 Sprint Retrospective | Actions for Sprint 3
SPRINT 2: MODEL OPTIMIZATION & API (Weeks 3-4) | 2.7 Sprint Retrospective | Sprint 2 retrospective notes
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.1 Sprint Planning (Day 1 of Sprint 3) | Sprint 3 goal defined
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.1 Sprint Planning (Day 1 of Sprint 3) | Sprint 3 backlog selected
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.1 Sprint Planning (Day 1 of Sprint 3) | Stories assigned
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.1 Sprint Planning (Day 1 of Sprint 3) | Sprint 3 backlog finalized
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | UI Design
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Wireframes/mockups reviewed
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | UI framework selected (React, Angular, Streamlit, Power Apps)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | UI components designed
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | UI Implementation
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Input forms created
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Prediction results display
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Explanation visualization
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | User feedback mechanism
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Error handling and validation
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | UI Testing
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Usability testing with sample users
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Feedback incorporated
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Accessibility checked
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | Working user interface
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.2 User Interface Development | UI connected to API
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Integration Points Identified
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Source systems (data inbound)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Target systems (predictions outbound)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Authentication systems
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Integration Implementation
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | API integrations developed
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Authentication/authorization implemented (Azure AD)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Data synchronization logic
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Error handling and retry logic
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Integration Testing
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | End-to-end integration tested
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Data flow validated
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Error scenarios tested
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | Integrations working
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.3 System Integration | End-to-end flow functional
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Application Monitoring
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Application Insights configured
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Custom metrics tracked
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Alerts configured
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Dashboard created
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Model Monitoring
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Prediction logging
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Model performance tracking
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Data drift detection setup
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Monitoring operational
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.4 Monitoring & Logging | Dashboards available
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.5 Daily Standups (Every Day) | Daily standups held
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.5 Daily Standups (Every Day) | Progress tracked
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | FULL END-TO-END PRESSURE TEST
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Business stakeholder operates the system live
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Real business scenario walkthrough
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | User enters data → System predicts → User sees explanation
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Integration with existing systems demonstrated live
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Monitoring and alerts shown
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Final Pressure Testing Questions
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | "Would you use this in your daily work?" (Business adoption test)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | "Does this deliver the expected value?" (Business value validation)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | "Can this go to production?" (Technical readiness test)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | "What's missing?" (Gap analysis)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | "Will users adopt this?" (Change management test)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | "Is this secure enough?" (Security validation)
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Go/No-Go Discussion
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Prototype success/failure assessed
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Build phase scope confirmed or adjusted
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Critical gaps identified for Build phase
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Sprint 3 demo completed
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Full pressure test validation
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.6 Sprint 3 PRESSURE TEST Demo (End of Week 6) | Go/No-Go recommendation for Build phase
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.7 Sprint Retrospective | Retrospective held
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.7 Sprint Retrospective | Lessons learned documented
SPRINT 3: UI/UX & INTEGRATION (Weeks 5-6) | 3.7 Sprint Retrospective | Sprint 3 retrospective notes
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.1 Sprint Planning | Sprint 4 goal defined
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.1 Sprint Planning | Remaining backlog items prioritized
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.1 Sprint Planning | Stories assigned
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Bug Fixes
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Known issues resolved
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Edge cases handled
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Performance optimizations
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | User Feedback
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Stakeholder feedback addressed
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | User experience improved
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Additional features (if time permits)
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Documentation
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Technical documentation completed
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | User guide drafted
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | API documentation finalized
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Architecture documentation updated
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Code Quality
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Code review completed
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Unit tests written (>70% coverage target)
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Code refactored
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Technical debt addressed
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Polished prototype
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.2 Refinement Activities | Documentation complete
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.3 Sprint 4 Demo & Retrospective | Final demo to stakeholders
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.3 Sprint 4 Demo & Retrospective | Retrospective held
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.3 Sprint 4 Demo & Retrospective | Overall prototype retrospective
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.3 Sprint 4 Demo & Retrospective | Sprint 4 demo completed
SPRINT 4 (OPTIONAL): REFINEMENT & POLISH (Weeks 7-8) | 4.3 Sprint 4 Demo & Retrospective | Project retrospective notes
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Functional Testing
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | All user stories tested
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Acceptance criteria validated
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Test cases documented
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Performance Testing
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | API latency measured
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Throughput tested
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Performance benchmarks met
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Security Testing
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Basic security scan performed
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Authentication tested
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Data access controls verified
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | User Acceptance Testing (Preliminary)
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Sample users test the prototype
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Feedback collected
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Critical issues resolved
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Test results documented
PROTOTYPE COMPLETION ACTIVITIES | 5.1 Prototype Testing | Known issues logged
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Technical Documentation
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Architecture diagram (updated)
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Data pipeline documentation
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Model documentation (algorithm, features, performance)
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | API documentation
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Deployment guide
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | User Documentation
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | User guide (draft)
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Demo scenarios
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | FAQ
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Code Documentation
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Code comments
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | README files
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Setup instructions
PROTOTYPE COMPLETION ACTIVITIES | 5.2 Prototype Documentation | Documentation package
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Pressure Test Results Compiled
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | What we proved: [List validated assumptions]
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | What we disproved: [List invalidated assumptions]
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | What we learned: [Key lessons]
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | What we pivoted: [Changes made during hackathon]
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Steering Committee Presentation
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Business stakeholders confirm value delivered
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Technical teams confirm architecture is sound
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Microsoft teams provide feedback and support
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Live prototype demonstration
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Pressure test results presented
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Build phase recommendations
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Key Questions Answered
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | "Did we validate the business requirements?" → Yes/No/Partially
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | "Did we validate the data quality?" → Yes/No/Partially
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | "Did we validate the ML approach?" → Yes/No/Partially
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | "Did we validate the architecture?" → Yes/No/Partially
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | "Did we validate business value?" → Yes/No/Partially
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Pressure test summary report
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Validated/invalidated assumptions list
PROTOTYPE COMPLETION ACTIVITIES | 5.3 Final Hackathon Pressure Test Summary | Build phase scope (adjusted based on learnings)
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Build Phase Planning
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Production readiness assessment
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Gaps identified (prototype vs. production)
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Build phase scope defined
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Build phase backlog created
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Knowledge Transfer
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Documentation handoff
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Code walkthrough for build team
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Architecture review
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Lessons learned shared
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Build phase plan
PROTOTYPE COMPLETION ACTIVITIES | 5.4 Handoff Planning | Handoff complete
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Readiness Assessment
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | All sprint demos completed
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Prototype functional
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Documentation complete
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Stakeholder feedback positive
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Phase Gate Presentation
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Prototype summary
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | What was built (features)
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Model performance achieved
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Technical approach validated
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | What was learned
HACKATHONS PHASE GATE REVIEW | 6.1 Phase Gate Preparation | Recommendation for Build phase
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | All previous phases PRESSURE TESTED
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Discovery findings validated with working code
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Business requirements proven with real prototype
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Data quality confirmed with actual ML pipeline
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Architecture validated with deployed components
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | ML approach proven with trained models
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Business Stakeholder Validation
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Business owners confirm: "This solves our problem"
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | End users confirm: "We would use this"
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Executives confirm: "This delivers expected value"
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Business value demonstrated (not just claimed)
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Technical Validation
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Architects confirm: "This architecture will scale"
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Engineers confirm: "This can be integrated"
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Security confirms: "This meets security requirements"
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Operations confirms: "This can be supported"
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Model performance meets business thresholds
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Microsoft Teams Validation
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | ATU/STU/FDE feedback incorporated
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Best practices validated
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Support model confirmed
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Pressure Test Outcomes
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Key assumptions validated or invalidated
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Lessons learned documented
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Pivots and adjustments made
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Build phase scope refined based on learnings
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Prototype Demonstrates
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | End-to-end working solution
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Real data processing
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Live predictions
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Business value (time saved, accuracy gained, cost reduced)
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Stakeholder Commitment
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Business Owner committed to Build phase
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Executive Sponsor approves continued investment
HACKATHONS PHASE GATE REVIEW | 6.2 Pressure Test Exit Criteria | Build phase budget secured
HACKATHONS PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Decision: GO / CONDITIONAL GO / ITERATE / NO-GO
HACKATHONS PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Conditions (if any): ___________
HACKATHONS PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Decision maker: ___________
HACKATHONS PHASE GATE REVIEW | 6.3 Go/No-Go Decision | Date: ___________
Key Metrics & Outcomes | Technical Achievements | Data pipeline operational
Key Metrics & Outcomes | Technical Achievements | Model trained and deployed
Key Metrics & Outcomes | Technical Achievements | API functional
Key Metrics & Outcomes | Technical Achievements | UI/UX implemented
Key Metrics & Outcomes | Technical Achievements | Integrations working
Key Metrics & Outcomes | Technical Achievements | Monitoring in place
Transition to Build Phase |  | Build Phase Kickoff Scheduled
Transition to Build Phase |  | Build Team Identified
Transition to Build Phase |  | Production Readiness Assessment
Transition to Build Phase |  | Hackathons Lessons Learned
Transition to Build Phase |  | Prototype Phase Closed