## 03 Setup Platform
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
PHASE GATE: Hackathons Complete |  | Hackathons phase completed successfully
PHASE GATE: Hackathons Complete |  | Working prototype demonstrated
PHASE GATE: Hackathons Complete |  | Go decision obtained from stakeholders
PHASE GATE: Hackathons Complete |  | Build phase scope confirmed
PHASE GATE: Hackathons Complete |  | Team ready (Platform Lead, DevOps, ML Engineers, QA)
PHASE GATE: Hackathons Complete |  | Budget and resources approved
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Azure Subscription Preparation
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Azure subscription identified or created
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Subscription naming: ___________
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Cost management configured
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Budget alerts set: $ ___________/month
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Tags defined (Environment, Project, Owner, CostCenter)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Resource Groups Created
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | DEV Resource Group: `rg-[project]-dev-[region]-01`
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | TEST Resource Group: `rg-[project]-test-[region]-01`
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | PROD Resource Group: `rg-[project]-prod-[region]-01`
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Shared Services RG (if needed): `rg-[project]-shared-[region]-01`
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Naming Conventions Documented
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Naming convention document created
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Examples provided for all resource types
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Team trained on naming conventions
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Azure subscriptions ready
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Resource groups created
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.1 Azure Subscription & Resource Group Setup | Naming conventions documented
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Virtual Network (VNet) Setup
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | DEV VNet created: `vnet-[project]-dev-[region]-01`
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | TEST VNet created: `vnet-[project]-test-[region]-01`
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | PROD VNet created: `vnet-[project]-prod-[region]-01`
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Subnets defined (compute, data, management)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Address spaces documented
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Network Security Groups (NSGs)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | NSGs created for each subnet
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Inbound rules configured (deny all by default)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Outbound rules configured
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Service tags used where appropriate
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | NSG flow logs enabled
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Azure Firewall / Application Gateway
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Firewall deployed (if required)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Application Gateway deployed (if required)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Firewall rules configured
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | WAF policies configured (if applicable)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Private Link / Service Endpoints
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Private Link configured for Azure ML
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Private Link configured for Storage
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Private Link configured for Key Vault
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Service Endpoints configured (if Private Link not used)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | VPN / ExpressRoute (if required)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | VPN Gateway configured
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Site-to-site connection established
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | On-premises connectivity tested
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Network Documentation
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Network topology diagram created
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | IP address allocation documented
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Security rules documented
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Network infrastructure operational
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Security rules enforced
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.2 Network & Security Foundation | Network diagram documented
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Azure AD Groups Created
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | `AI-Project-Admins` group
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | `AI-Project-Developers` group
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | `AI-Project-DataScientists` group
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | `AI-Project-QA` group
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | `AI-Project-Operations` group
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | `AI-Project-BusinessUsers` group
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | RBAC Roles Assigned
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Admins: Owner/Contributor on resource groups
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Developers: Contributor on DEV resources
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Data Scientists: Azure ML Contributor
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | QA: Reader on TEST, Contributor on test resources
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Operations: Contributor on PROD
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Business Users: Custom role (read-only access)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Managed Identities
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | System-assigned identities enabled for Azure resources
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | User-assigned identities created (if needed)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Managed identity permissions assigned
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Conditional Access Policies
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | MFA required for all admin accounts
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | MFA required for production access
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Location-based restrictions (if required)
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Device compliance requirements
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Service Principals
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Service principal for CI/CD pipelines
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Service principal for automation scripts
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Certificates/secrets configured and stored in Key Vault
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | IAM structure implemented
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | All users have appropriate access
WEEK 1: INFRASTRUCTURE SETUP & ENVIRONMENT PROVISIONING | 1.3 Identity & Access Management (IAM) | Managed identities configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Azure ML Workspaces Created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | DEV Workspace: `mlw-[project]-dev-[region]-01`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | TEST Workspace: `mlw-[project]-test-[region]-01`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | PROD Workspace: `mlw-[project]-prod-[region]-01`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Workspace identity configured (System-assigned or User-assigned)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Associated Resources
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Storage Account created for each workspace
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Key Vault created for each workspace
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Application Insights created for each workspace
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Container Registry created (shared or per workspace)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Compute Resources
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Training compute cluster created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Inference compute cluster created (if using managed endpoints)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Compute instances for development (optional)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Datastores Configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Default datastore verified
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Additional datastores registered (if needed)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Data Lake Gen2 connected
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | On-premises data sources connected (if needed)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Private Endpoints
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Private endpoint for workspace
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Private endpoint for storage
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Private endpoint for container registry
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | DNS zones configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Azure ML workspaces operational in all environments
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Compute resources provisioned
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.1 Azure ML Workspace Setup | Datastores connected
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Azure Data Lake Gen2
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Storage account created: `st[project][env]01`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Hierarchical namespace enabled
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Containers created: `raw`, `processed`, `features`, `models`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Access control configured (RBAC + ACLs)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Lifecycle management policies configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Azure Data Factory (ADF)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | ADF instance created: `adf-[project]-[env]-01`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Git integration configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Linked services created (sources, sinks)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Self-hosted integration runtime (if needed)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Managed VNet configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data Pipelines
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data ingestion pipeline created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data cleansing pipeline created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Feature engineering pipeline created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data quality checks implemented
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Pipeline triggers configured (schedule, event-based)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data Governance
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data classification implemented
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data lineage tracking configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | PII detection configured (if applicable)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data retention policies configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data platform operational
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data pipelines running successfully
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.2 Data Platform Setup | Data governance implemented
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Azure DevOps / GitHub Setup
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Project/repository created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Branch strategy defined (main, develop, feature branches)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Branch policies configured (require PR, code review)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Service connections created (Azure ML, Azure subscription)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Training Pipeline YAML
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Pipeline YAML file created: `.azuredevops/train-pipeline.yml`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Trigger configured (manual, scheduled, code changes)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Variables and variable groups configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Secrets stored in Azure DevOps Library / GitHub Secrets
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Training Pipeline Steps
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Step 1: Environment setup (install dependencies)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Step 2: Data preparation (load and preprocess data)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Step 3: Model training (train model)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Step 4: Model evaluation (evaluate against test set)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Step 5: Model validation (check performance thresholds)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Step 6: Model registration (register in Model Registry if validation passes)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Step 7: Artifact publishing (publish model artifacts)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Quality Gates
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Model accuracy threshold: ____%
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Code coverage threshold: ____%
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Linting and code quality checks
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Security scanning (dependencies, secrets)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Pipeline Testing
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Training pipeline executed successfully in DEV
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Model registered in Azure ML
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Artifacts published
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Training pipeline operational
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Automated model training working
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.3 CI/CD Pipeline for Model Training | Model versioning implemented
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Deployment Pipeline YAML
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Pipeline YAML file created: `.azuredevops/deploy-pipeline.yml`
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Trigger: On successful training pipeline completion
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Multi-stage pipeline (DEV → TEST → PROD)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Deployment Pipeline Stages
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Model downloaded from registry
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Endpoint created/updated in DEV
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Smoke tests executed
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Auto-proceed to next stage
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Model deployed to TEST endpoint
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Integration tests executed
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Manual approval gate configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Approval required from QA team
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Blue-green deployment strategy
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Deploy to staging slot (blue)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Smoke tests on staging
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Manual approval gate configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Approval required from Ops + Business
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Traffic switch to new version (green)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Monitor for 1 hour
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Rollback procedure if issues detected
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Deployment Strategies
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Blue-green deployment configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Canary deployment option available (optional)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | A/B testing capability (optional)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Rollback Mechanism
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Previous model version tagged
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Rollback script created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Rollback tested in DEV
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Pipeline Testing
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Deployment pipeline executed successfully
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Model deployed to all environments
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Approval gates working
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Deployment pipeline operational
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Multi-stage deployment working
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.4 CI/CD Pipeline for Model Deployment | Rollback capability validated
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Application Insights Configuration
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Application Insights instances created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Connected to Azure ML workspace
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Custom metrics configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Model Performance Monitoring
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Accuracy tracking enabled
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Precision, Recall, F1 tracking
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Comparison to baseline model
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Performance degradation alerts configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Data Drift Detection
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Input feature drift monitoring enabled
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Drift thresholds configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Drift alerts configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Comparison dataset registered (training data)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Prediction Drift Monitoring
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Output distribution tracking
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Anomaly detection configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Prediction drift alerts
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Operational Metrics
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Inference latency tracking
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Request volume tracking
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Error rate tracking
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Resource utilization tracking
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Dashboards
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Model performance dashboard created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Data drift dashboard created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Operational metrics dashboard created
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Dashboards shared with Ops team
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Alerting Rules
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Alert: Model accuracy drops >5%
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Alert: Data drift detected
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Alert: Error rate >1%
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Alert: Latency >100ms (P95)
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Alert recipients configured
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Model monitoring operational
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Dashboards available
WEEK 2: MLOPS PIPELINE IMPLEMENTATION | 2.5 Model Monitoring Setup | Alerts configured and tested
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Secrets Management
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Azure Key Vault created for each environment
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | All secrets migrated to Key Vault
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | No hardcoded secrets in code (verified)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Key Vault access policies configured
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Secret rotation policy defined
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Network Security
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Public access disabled where possible
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Private Link enabled for all Azure services
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Service endpoints configured (fallback)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | NSG rules reviewed and minimized
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | DDoS protection enabled (PROD)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Data Encryption
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Encryption at rest enabled (all storage)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Encryption in transit enforced (TLS 1.2+)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Customer-managed keys configured (if required)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Key rotation schedule defined
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Audit Logging
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Diagnostic logs enabled on all resources
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Logs sent to Log Analytics workspace
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Log retention policy: _____ days
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Audit log review process defined
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | API Security
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | API Management configured (if used)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | API authentication enabled (OAuth 2.0 / API keys)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Rate limiting configured
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | IP whitelisting configured (if required)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | CORS policies configured
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Security controls implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | All secrets in Key Vault
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.1 Security Hardening | Audit logging enabled
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Azure Policy Implementation
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Policy: Enforce resource tagging
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Policy: Enforce encryption at rest
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Policy: Deny public IP addresses
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Policy: Enforce approved VM SKUs
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Policy: Enforce naming conventions
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Policies assigned to resource groups/subscription
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Compliance Assessment
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Azure Security Center compliance scan run
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Compliance standard: ___________
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Compliance score: _____%
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Critical issues documented: _____
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Remediation plan for gaps
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data Governance
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data classification implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | PII fields identified and tagged
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data lineage tracking configured
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data retention policies configured
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data deletion process defined
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Regulatory Compliance (if applicable)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data minimization principles applied
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Right to access implemented (data subject requests)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Right to erasure implemented (right to be forgotten)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Right to data portability implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Consent management implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data processing agreements in place
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Privacy by design and by default
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data breach notification process (72 hours)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data Protection Impact Assessment (DPIA) completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | GDPR compliance documentation completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | PHI (Protected Health Information) identified
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | PHI encryption at rest and in transit
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Access controls for PHI (minimum necessary principle)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Audit controls implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Integrity controls implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Transmission security implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Business Associate Agreements (BAAs) in place
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | HIPAA Security Rule compliance documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | HIPAA Privacy Rule compliance documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Breach notification procedures documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Security controls documented and implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Availability controls implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Processing integrity controls implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Confidentiality controls implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Privacy controls implemented (if applicable)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Access reviews conducted regularly
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Change management process documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Incident response plan documented and tested
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Vendor risk management process
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | SOC 2 audit preparation completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Cardholder data environment (CDE) identified and segmented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 1: Install and maintain firewall configuration
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Firewall rules documented and reviewed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Network segmentation implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 2: Do not use vendor-supplied defaults
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Default passwords changed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Unnecessary services disabled
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 3: Protect stored cardholder data
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Cardholder data encrypted (AES-256 or equivalent)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Encryption key management process
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Cardholder data retention policy (minimize storage)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | PAN (Primary Account Number) masking implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 4: Encrypt transmission of cardholder data
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | TLS 1.2+ for all transmissions
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Strong cryptography protocols
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 5: Protect against malware
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Anti-malware solutions deployed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Regular malware scans
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 6: Develop secure systems and applications
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Secure development lifecycle implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Code reviews conducted
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Vulnerability scanning completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Penetration testing completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 7: Restrict access by business need-to-know
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Role-based access control (RBAC) implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Least privilege principle enforced
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 8: Identify and authenticate access
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Multi-factor authentication (MFA) for all access
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Strong password policies
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | User account management process
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 9: Restrict physical access (if applicable)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 10: Track and monitor all access
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Audit logging enabled for all cardholder data access
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Log retention: minimum 1 year
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Logs reviewed regularly
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 11: Regularly test security systems
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Quarterly vulnerability scans
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Annual penetration testing
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | File integrity monitoring
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Requirement 12: Maintain information security policy
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Security policy documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Annual security awareness training
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Incident response plan
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | PCI-DSS Self-Assessment Questionnaire (SAQ) completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Attestation of Compliance (AOC) obtained (if required)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Quarterly PCI scans scheduled with ASV (Approved Scanning Vendor)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | CPS 234 Information Security Requirements
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Information security capability maintained commensurate with threats
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Board-level oversight of information security
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Information security controls implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Systematic testing and assurance of information security
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Information Asset Classification
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Information assets identified and classified
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Criticality assessment completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Protection measures aligned with criticality
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Access Management
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | User access management controls
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Privileged access management implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Access reviews conducted regularly (at least annually)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Segregation of duties implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Incident Management
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Incident response plan documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Incident notification to APRA (within 72 hours for material incidents)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Incident register maintained
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Post-incident reviews conducted
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Third-Party/Outsourcing Risk
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Material outsourcing arrangements identified
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Due diligence on service providers completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Contractual protections in place
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Right to audit service providers
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Service provider security assessments conducted
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Business Continuity and Disaster Recovery
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Business continuity plan documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Disaster recovery plan documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Recovery time objectives (RTO) defined: _____ hours
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Recovery point objectives (RPO) defined: _____ hours
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | BC/DR testing conducted (at least annually)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Testing and Assurance
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Vulnerability assessments conducted regularly
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Penetration testing conducted (at least annually)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Security control effectiveness reviews
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Independent assurance reviews (if material arrangement)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data Residency and Sovereignty
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data stored in Australian regions (if required)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Cross-border data flow assessment
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data sovereignty requirements documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Notification and Reporting
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Material information security incident notification process
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | APRA notification template prepared
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Board reporting on information security (at least annually)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | APRA CPS 234 compliance self-assessment completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | APRA reporting obligations documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Annual information security attestation prepared
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Azure Policies enforced
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Compliance gaps identified and remediated
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Data governance implemented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.2 Compliance & Governance | Regulatory compliance requirements met and documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | API Integration Tests
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: API authentication/authorization
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Valid prediction request (happy path)
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Invalid input handling
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Error response formats
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Rate limiting behavior
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Concurrent requests
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | All tests passing: Yes ☐ No ☐
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Data Pipeline Integration Tests
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Data ingestion from source systems
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Data quality checks
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Feature engineering
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Data refresh scenarios
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Failure handling
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | All tests passing: Yes ☐ No ☐
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | ML Pipeline Integration Tests
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: End-to-end model training
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Model registration
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Model deployment
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Model scoring
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Model monitoring data flow
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | All tests passing: Yes ☐ No ☐
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | External System Integration Tests
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Integration with System A: ___________
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Integration with System B: ___________
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test: Integration with System C: ___________
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Authentication with external systems working
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | All tests passing: Yes ☐ No ☐
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test Results Documentation
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test plan documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test cases documented
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Test results recorded
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Defects logged and tracked
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Integration test suite completed
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | All critical integration tests passing
WEEK 3: SECURITY, COMPLIANCE & INTEGRATION TESTING | 3.3 Integration Testing | Integration issues resolved
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Load Test Preparation
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Load testing tool selected (Azure Load Testing, JMeter, etc.)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test scenarios defined
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test data prepared
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test environment ready (TEST environment)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Scenario 1: Normal Load
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Concurrent users: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Requests per second: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test duration: _____ minutes
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Target P95 latency: < _____ ms
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test executed: Yes ☐ No ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Results: Pass ☐ Fail ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | P95 latency achieved: _____ ms
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Error rate: _____% (target: <0.1%)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Scenario 2: Peak Load
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Concurrent users: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Requests per second: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test duration: _____ minutes
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Target P95 latency: < _____ ms
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test executed: Yes ☐ No ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Results: Pass ☐ Fail ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | P95 latency achieved: _____ ms
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Error rate: _____% (target: <1%)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Scenario 3: Stress Test
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Concurrent users: _____ (2x peak)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Requests per second: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test duration: _____ minutes
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Goal: Identify breaking point
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test executed: Yes ☐ No ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | System remained stable: Yes ☐ No ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Breaking point identified: _____ requests/sec
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Model Inference Performance
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Single prediction latency: _____ ms (target: <50ms)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Batch prediction throughput: _____ predictions/sec
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Concurrent request handling tested
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Performance meets requirements: Yes ☐ No ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Performance Test Report
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Test results documented
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Performance baseline established
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Bottlenecks identified
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Recommendations documented
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Load tests completed
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Performance baseline established
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.1 Performance Testing | Bottlenecks identified
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | API Optimization
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Caching implemented (Redis, in-memory)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Database query optimization
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Connection pooling configured
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | CDN configured (if serving static content)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Compression enabled (gzip)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Model Optimization
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Model quantization (if applicable)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Batch processing optimization
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Inference parallelization
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | GPU acceleration enabled (if beneficial)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Model size optimized
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Auto-Scaling Configuration
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Horizontal auto-scaling rules configured
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Scale-out trigger: CPU >____%
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Scale-in trigger: CPU <____%
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Min instances: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Max instances: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Auto-scaling tested under load
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Post-Optimization Testing
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Load tests re-run after optimization
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Performance improvements measured
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Before optimization P95 latency: _____ ms
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | After optimization P95 latency: _____ ms
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Performance targets met: Yes ☐ No ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Performance optimizations implemented
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Auto-scaling configured and tested
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.2 Performance Optimization | Performance targets met
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Failure Scenario Testing
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Test: API service unavailable
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Test: Database connection failure
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Test: Model endpoint failure
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Test: Data pipeline failure
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Test: Network partition
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Graceful degradation verified
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Circuit Breaker Implementation
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Circuit breaker pattern implemented
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Fallback logic defined
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Circuit breaker tested
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Retry Logic
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Retry mechanism implemented (exponential backoff)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Max retry attempts: _____
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Retry tested under failure scenarios
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Disaster Recovery Testing
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Backup and restore tested
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Failover to secondary region tested (if multi-region)
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | RTO (Recovery Time Objective): _____ hours
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | RPO (Recovery Point Objective): _____ hours
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | RTO/RPO targets met: Yes ☐ No ☐
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Resilience tests completed
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | Failure handling verified
WEEK 4: PERFORMANCE TESTING & OPTIMIZATION | 4.3 Resilience & Chaos Testing | DR procedures validated
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT Environment Setup
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Latest version deployed to TEST environment
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Production-like data loaded (anonymized)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | User accounts created for business testers
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT tracking tool configured (Azure DevOps Test Plans)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT Test Cases Creation
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Business scenario test cases created
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | End-to-end workflow test cases
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Edge case scenarios documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Error handling scenarios documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Total test cases: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT Kickoff
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT kickoff meeting scheduled: ___________
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Business users identified and invited
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT process explained
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Test case review completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Issue reporting process explained
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT environment ready
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | UAT test cases documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.1 UAT Preparation | Business testers trained
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Test Execution
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | UAT start date: ___________
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | UAT end date: ___________
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Test cases executed: _____/_____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Test cases passed: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Test cases failed: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Test cases blocked: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Daily UAT Standups
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Daily standup meeting scheduled
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Progress tracked daily
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Blockers resolved daily
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Defect Management
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Total defects logged: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Critical defects: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | High defects: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Medium defects: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Low defects: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Defects resolved: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Defects remaining: _____
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Regression Testing
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Regression tests executed after bug fixes
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | No new issues introduced by fixes
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | UAT test execution completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Defects logged and tracked
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.2 UAT Execution | Critical/high priority defects resolved
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Defect Resolution
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | All critical defects resolved
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | All high defects resolved (or accepted with workarounds)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Medium/low defects documented in known issues list
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | UAT Summary Report
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Test execution summary documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Defect summary documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Known issues documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Test coverage: _____% (target: >95%)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Pass rate: _____% (target: >95%)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | UAT Sign-off Meeting
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Meeting scheduled: ___________
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Business stakeholders present
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | UAT results presented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Known issues reviewed and accepted
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Formal sign-off obtained: Yes ☐ No ☐
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Sign-off document signed by: ___________
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | UAT sign-off obtained
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Known issues documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.3 UAT Sign-off | Business approval secured
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Production Readiness Checklist
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | All required features implemented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | All critical bugs resolved
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Known issues documented and accepted
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Performance benchmarks met
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Load testing completed successfully
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Auto-scaling validated
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Security review completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Penetration testing completed and passed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | All secrets in Key Vault
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Audit logging enabled and tested
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Compliance requirements met
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Data privacy controls implemented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Regulatory approvals obtained (if needed)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Monitoring and alerting configured
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Dashboards created and shared
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Alert testing completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Operations runbook completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | On-call rotation established
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Incident response plan documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Backup and recovery tested
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Architecture documentation complete
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | API documentation complete
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | User documentation complete
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Operations runbook complete
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Deployment guide complete
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Operations team trained
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Support team trained
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | End users trained (if needed)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Deployment plan documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Rollback plan documented
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Communication plan ready
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Deployment window scheduled: ___________
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Change request approved (if required)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Go/No-Go Meeting
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Meeting scheduled: ___________
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | All stakeholders invited:
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Executive Sponsor
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Product Owner
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Platform Lead
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | DevOps Lead
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Security Lead
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Operations Lead
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Business Stakeholders
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Production readiness checklist reviewed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Risks and mitigations reviewed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Go-Live decision: GO ☐ NO-GO ☐ CONDITIONAL GO ☐
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Production readiness checklist 100% complete
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Go-Live approval obtained
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.4 Production Readiness Review | Deployment date confirmed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Architecture Documentation
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Architecture diagrams (current state)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Component descriptions
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Data flow diagrams
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Security architecture
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Network topology
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Operations Runbook
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Start/stop procedures
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Monitoring procedures
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Alert response procedures
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Common troubleshooting scenarios
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Escalation procedures
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Disaster recovery procedures
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Deployment Guide
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Deployment prerequisites
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Deployment steps
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Rollback steps
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Post-deployment verification
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Deployment checklist
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | User Documentation
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | User guide / manual
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | FAQ document
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Training materials
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Video tutorials (if applicable)
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Knowledge Transfer
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Handoff session with Operations team completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Handoff session with Support team completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Q&A session completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | All questions addressed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Complete documentation package
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Knowledge transfer completed
WEEK 5-6: USER ACCEPTANCE TESTING (UAT) & PRODUCTION READINESS | 5.5 Final Documentation & Handoff | Operations team ready
PHASE EXIT CRITERIA |  | ✅ All environments (DEV, TEST, PROD) provisioned and operational
PHASE EXIT CRITERIA |  | ✅ MLOps pipelines (training & deployment) working end-to-end
PHASE EXIT CRITERIA |  | ✅ All security controls implemented and validated
PHASE EXIT CRITERIA |  | ✅ Compliance requirements met and documented
PHASE EXIT CRITERIA |  | ✅ All integration tests passing (>95% pass rate)
PHASE EXIT CRITERIA |  | ✅ Performance benchmarks met (latency, throughput, availability)
PHASE EXIT CRITERIA |  | ✅ UAT completed and signed off by business
PHASE EXIT CRITERIA |  | ✅ Production readiness checklist 100% complete
PHASE EXIT CRITERIA |  | ✅ All documentation completed
PHASE EXIT CRITERIA |  | ✅ Operations team trained and ready
PHASE EXIT CRITERIA |  | ✅ Go-Live approval obtained from all stakeholders
PHASE EXIT CRITERIA |  | ✅ Deployment date confirmed