## 04 Build Phase
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
PHASE GATE: Setup Platform Complete |  | Setup Platform phase completed successfully
PHASE GATE: Setup Platform Complete |  | All environments (DEV, TEST, PROD) operational
PHASE GATE: Setup Platform Complete |  | MLOps pipelines working
PHASE GATE: Setup Platform Complete |  | Security and compliance requirements met
PHASE GATE: Setup Platform Complete |  | Platform ready for development
PHASE GATE: Setup Platform Complete |  | Development team ready
PHASE GATE: Setup Platform Complete |  | Product backlog prioritized
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Build Phase Kickoff Meeting
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Meeting date: ___________
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | All team members present
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Stakeholders present
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Project vision and objectives reviewed
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Sprint schedule communicated
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Ways of working agreed
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Team Setup
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Team roles and responsibilities defined
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Development environment access verified for all
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Communication channels established (Teams, Slack)
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Daily standup time scheduled: ___________
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Sprint ceremonies scheduled
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Product Backlog Preparation
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | All user stories defined
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Acceptance criteria documented
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Stories prioritized (MoSCoW: Must, Should, Could, Won't)
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Dependencies identified
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Stories estimated (story points)
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Sprint 1 backlog ready
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Project kickoff completed
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Team aligned and ready
SPRINT 0: BUILD PHASE KICKOFF | 0.1 Project Kickoff | Product backlog ready
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Sprint Goal Defined
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Sprint goal: ___________________________________________
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Goal communicated to all team members
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Sprint Backlog Created
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | User stories selected for Sprint 1
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Total story points: _____ (team capacity: _____)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Stories broken down into tasks
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Tasks assigned to team members
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Sprint Commitment
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Team commits to sprint goal
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Definition of Done reviewed and agreed
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.1 Sprint Planning (Day 1) | Sprint backlog finalized
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Daily Standups
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 2 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 3 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 4 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 5 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 6 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 7 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 8 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Day 9 standup completed ☐
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Model Development
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Production model trained with full dataset
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Hyperparameter optimization completed
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Model validation on test set
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Model performance meets minimum threshold: _____% accuracy
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Model explainability implemented (SHAP/LIME)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Model registered in Azure ML Model Registry
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Model version: ___________
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Model performance documented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | API Development
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Prediction API endpoint implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Input validation implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Error handling implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Response formatting implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | API versioning implemented (v1)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | API documentation (Swagger/OpenAPI)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | API unit tests (>80% coverage)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | UI Development
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | UI wireframes/mockups approved
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Prediction input form implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Results display implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Explanation visualization implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Error messaging implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Responsive design (mobile, tablet, desktop)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Data Pipeline
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Production data pipeline implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Data quality monitoring implemented
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Feature engineering automated
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Data refresh scheduling configured
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Data pipeline testing completed
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | CI/CD Pipeline
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Automated build on commit
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Automated tests on build
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Automated deployment to DEV
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Pipeline runs successfully
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Code Quality
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Code reviews completed for all PRs
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | No critical code quality issues
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | Code coverage >80%
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.2 Development Activities (Days 2-9) | All automated tests passing
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Demo Preparation
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Demo environment ready
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Demo data prepared
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Demo script prepared
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Sprint Review Meeting
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Meeting date: ___________
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Stakeholders present
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Sprint goal reviewed
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Live demonstration completed
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Stakeholder feedback collected
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Product backlog updated based on feedback
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Model training process demonstrated
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | Prediction API demo (Postman/Swagger)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | UI walkthrough (input → predict → results → explanation)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.3 Sprint Review (Day 10) | End-to-end scenario demonstrated
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | Retrospective Meeting
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | Meeting date: ___________
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | All team members present
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | What went well? (documented)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | What didn't go well? (documented)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | Action items identified (max 3)
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | Action item owners assigned
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | Sprint 1 completed
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | Sprint velocity recorded: _____ points
WEEKS 1-2: SPRINT 1 - CORE FEATURES DEVELOPMENT | 1.4 Sprint Retrospective (Day 10) | Retrospective action items documented
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.1 Sprint Planning (Day 1) | Sprint Goal Defined
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.1 Sprint Planning (Day 1) | Sprint goal: ___________________________________________
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.1 Sprint Planning (Day 1) | Sprint Backlog Created
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.1 Sprint Planning (Day 1) | User stories selected for Sprint 2
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.1 Sprint Planning (Day 1) | Total story points: _____
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.1 Sprint Planning (Day 1) | Stories broken down into tasks
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.1 Sprint Planning (Day 1) | Tasks assigned
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Daily Standups (8 standups completed) ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Integration Development
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Source system integration 1: ___________ ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Source system integration 2: ___________ ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Target system integration 1: ___________ ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Target system integration 2: ___________ ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Authentication with external systems ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Data synchronization logic ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Error handling and retry logic ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Integration testing completed ☐
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Advanced Features
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Batch prediction capability
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Model comparison (champion vs challenger)
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Advanced explainability features
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | User preferences and settings
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Notification system (email/Teams)
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Export functionality (CSV, PDF)
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Monitoring & Observability
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Application Insights integration complete
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Custom metrics implemented:
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Prediction volume
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Prediction latency
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Model accuracy (actual vs predicted)
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Error rates
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Performance dashboards created
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Alerting rules configured:
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | High error rate alert
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | High latency alert
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Model performance degradation alert
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Data quality alert
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Health check endpoint implemented
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Security Enhancements
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Authentication implemented (Azure AD / OAuth 2.0)
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Authorization implemented (RBAC)
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Input sanitization implemented
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Rate limiting configured
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Security headers configured
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | CORS policies configured
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Code Quality
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | All code reviewed
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | Code coverage >80%
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.2 Development Activities (Days 2-9) | All tests passing
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Sprint Review Completed
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Integration demos completed
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Advanced features demonstrated
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Monitoring dashboards shown
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Stakeholder feedback collected
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Sprint Retrospective Completed
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Action items from Sprint 1 reviewed
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Sprint 2 retrospective conducted
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | New action items documented
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Sprint 2 completed
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Sprint velocity: _____ points
WEEKS 3-4: SPRINT 2 - ADVANCED FEATURES & INTEGRATIONS | 2.3 Sprint Review & Retrospective (Day 10) | Cumulative velocity: _____ points
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.1 Sprint Planning (Day 1) | Sprint Goal Defined
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.1 Sprint Planning (Day 1) | Sprint goal: Polish features, fix bugs, comprehensive testing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.1 Sprint Planning (Day 1) | Sprint Backlog Created
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.1 Sprint Planning (Day 1) | Bug fixes prioritized
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.1 Sprint Planning (Day 1) | Polish tasks identified
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.1 Sprint Planning (Day 1) | Testing tasks planned
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.1 Sprint Planning (Day 1) | Total story points: _____
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Daily Standups (8 standups completed) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | UI/UX Polish
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | UI design refinements based on feedback
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Accessibility improvements (WCAG 2.1 Level AA)
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Keyboard navigation
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Screen reader compatibility
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Color contrast ratios
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Alt text for images
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Responsive design validated (mobile, tablet, desktop)
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Performance optimization:
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Lazy loading implemented
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Caching strategy implemented
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Bundle size optimized
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Image optimization
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | User experience improvements
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Bug Fixing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | All critical bugs resolved
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | All high priority bugs resolved
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Medium/low bugs addressed (or deferred)
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Technical debt items addressed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Code refactoring completed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Testing Activities
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | End-to-end test scenarios defined
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | End-to-end tests automated
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | All integration tests passing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Integration test report generated
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Load test scenarios defined
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Load testing tool configured (Azure Load Testing/JMeter)
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Normal load test executed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Target: 1000 req/sec, P95 latency <100ms
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Result: Pass ☐ Fail ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Peak load test executed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Target: 2000 req/sec, P95 latency <200ms
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Result: Pass ☐ Fail ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Stress test executed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Breaking point identified: _____ req/sec
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Performance test report generated
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | OWASP Top 10 testing:
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | SQL Injection testing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Cross-Site Scripting (XSS) testing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Cross-Site Request Forgery (CSRF) testing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Authentication testing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Authorization testing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Security misconfiguration testing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | SAST (Static Application Security Testing) scan
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Critical vulnerabilities: 0
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | High vulnerabilities: 0
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | DAST (Dynamic Application Security Testing) scan
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Critical vulnerabilities: 0
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | High vulnerabilities: 0
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Dependency vulnerability scan
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Security test report generated
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Browser testing:
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Chrome (latest) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Firefox (latest) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Safari (latest) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Edge (latest) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Device testing:
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Desktop (Windows, Mac) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Tablet (iPad, Android) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Mobile (iPhone, Android) ☐
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Regression test suite defined
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | All regression tests executed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | All regression tests passing
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | No new defects introduced
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Documentation
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | API documentation complete and accurate
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | User documentation draft completed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Technical documentation updated
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.2 Development Activities (Days 2-9) | Operations runbook draft completed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Sprint Review Completed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Polished UI demonstrated
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Bug fixes demonstrated
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Test results presented
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Documentation reviewed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Sprint Retrospective Completed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Sprint 3 completed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Sprint velocity: _____ points
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | All testing completed
WEEKS 5-6: SPRINT 3 - POLISH, REFINEMENT & TESTING | 3.3 Sprint Review & Retrospective (Day 10) | Quality gates met
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | UAT Environment Setup
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Latest version deployed to TEST environment
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Production-like data loaded (anonymized)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | User accounts created for business testers
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | UAT tracking tool configured (Azure DevOps Test Plans)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | UAT Test Cases Creation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Business scenario test cases created
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | End-to-end workflow test cases created
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Edge case scenarios documented
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Error handling scenarios documented
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Total test cases: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Test cases reviewed and approved
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | UAT Kickoff
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | UAT kickoff meeting date: ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Business users identified and invited
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | UAT process explained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Test case walkthrough completed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | Issue reporting process explained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.1 UAT Preparation (Week 7, Days 1-2) | UAT schedule communicated
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | UAT Testing
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | UAT start date: ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | UAT end date: ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Test cases executed: _____/_____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Test cases passed: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Test cases failed: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Test cases blocked: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Pass rate: _____% (target: >95%)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Daily UAT Standups
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Daily standup meetings held
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Progress tracked daily
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Blockers resolved daily
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Defect Management
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Total defects logged: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Critical defects: _____ (all must be resolved)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | High defects: _____ (all must be resolved or have workarounds)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Medium defects: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Low defects: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Defects resolved: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Defects remaining: _____
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Known issues documented
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Regression Testing
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | Regression tests executed after bug fixes
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | All regression tests passing
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.2 UAT Execution (Week 7, Days 3-5; Week 8, Days 1-3) | No new issues introduced
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Defect Resolution Validation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | All critical defects resolved
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | All high defects resolved or accepted with workarounds
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Medium/low defects accepted or scheduled for post-release
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | UAT Summary Report
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Test execution summary documented
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Defect summary documented
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Known issues list documented
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Test coverage achieved: _____% (target: >95%)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Overall pass rate: _____% (target: >95%)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | UAT Sign-off Meeting
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Meeting date: ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Business stakeholders present
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | UAT results presented
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Known issues reviewed and accepted
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Formal UAT sign-off obtained: Yes ☐ No ☐
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Sign-off document signed by: ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | UAT completed successfully
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | UAT sign-off obtained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.3 UAT Sign-off (Week 8, Day 4) | Production readiness validated by business
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training Materials Preparation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | User guide completed (with screenshots)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Video tutorials created:
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Getting started video (5 min)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Feature walkthrough videos (5-10 min each)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Quick reference guide (1-2 pages)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | FAQ document
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training presentation deck
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Hands-on lab exercises
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Support guide completed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Troubleshooting guide
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Common issues and resolutions
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Escalation procedures
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Operations runbook completed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Monitoring guide
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Incident response procedures
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | DR procedures
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training Sessions Scheduled
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | End user training sessions: _____ sessions
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Support team training sessions: _____ sessions
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Operations team training sessions: _____ sessions
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training Delivery
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Session 1 date: ___________ (Attendees: _____)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Session 2 date: ___________ (Attendees: _____)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Session 3 date: ___________ (Attendees: _____)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Additional sessions as needed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training feedback collected
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training effectiveness: _____/5 (target: >4/5)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training date: ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | All support team members trained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Knowledge check passed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Training date: ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | All operations team members trained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Runbook walkthrough completed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Monitoring and alerting demonstrated
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Incident response walkthrough completed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Train-the-Trainer
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Champions identified: ___________, ___________, ___________
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Champions trained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Champions can train others
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | All training materials completed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | All training sessions delivered
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | >90% of target users trained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.4 Training Delivery (Week 8) | Support and operations teams ready
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | User Documentation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | User guide finalized and reviewed
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Video tutorials published (LMS/YouTube/SharePoint)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Quick reference guide finalized
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | FAQ document finalized
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | All documentation accessible to users
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Technical Documentation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Architecture documentation finalized
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | API documentation finalized
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Data model documentation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Integration documentation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Code documentation (inline comments, README)
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Operations Documentation
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Operations runbook finalized
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Monitoring and alerting guide
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Troubleshooting guide
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Incident response plan
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Disaster recovery procedures
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Backup and restore procedures
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Documentation Review
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | All documentation reviewed by SMEs
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Feedback incorporated
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Final approval obtained
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Complete documentation package
WEEKS 7-8: SPRINT 4 - UAT, TRAINING & DOCUMENTATION | 4.5 Documentation Finalization (Week 8) | Documentation published and accessible
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Final Regression Testing
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | All test cases re-executed in TEST environment
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | All test cases passing
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | No critical or high severity bugs
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Test results documented
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Security Final Review
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Final security scan (SAST/DAST)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Penetration testing results reviewed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | All critical/high vulnerabilities resolved
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Security sign-off obtained: Yes ☐ No ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Signed off by: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Compliance Final Review
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Compliance requirements verified
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Audit logs tested
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Data privacy controls verified
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Compliance sign-off obtained: Yes ☐ No ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Signed off by: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Performance Validation
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Load testing in PROD-like environment
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Performance benchmarks met:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | API P95 latency: _____ ms (target: <100ms)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Model inference: _____ ms (target: <50ms)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Page load time: _____ sec (target: <3sec)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Throughput: _____ req/sec (target: 1000+)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Auto-scaling validated
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Performance test report generated
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Disaster Recovery Testing
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Backup and restore tested
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Failover tested (if multi-region)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | RTO validated: _____ hours (target: _____)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | RPO validated: _____ hours (target: _____)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | DR test report generated
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | All final testing completed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | All quality gates passed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.1 Final Testing & Validation (Week 9) | Sign-offs obtained
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Deployment Plan Finalized
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Deployment approach selected:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Blue-Green ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Canary ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Rolling ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Deployment steps documented in detail
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Deployment window selected:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Date: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Time: ___________ (recommend off-peak hours)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Duration estimate: _____ hours
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Change request submitted
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Change request approved: Yes ☐ No ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Change request number: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Rollback Plan Documented
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Rollback triggers defined
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Rollback procedure documented step-by-step
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Rollback tested in TEST environment
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Rollback time estimate: _____ minutes (target: <15 min)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Rollback decision makers identified
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Communication Plan
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Stakeholder communication plan
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | User communication plan
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Deployment notification email drafted
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Post-deployment notification email drafted
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Downtime communication (if applicable)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Communication schedule:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | 1 week before: Announcement
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | 3 days before: Reminder
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | 1 day before: Final reminder
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Deployment day: Status updates
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Day after: Success confirmation
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Hypercare Planning
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Hypercare duration: _____ days (recommend 7-14 days)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Hypercare team identified:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Product Owner: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Technical Lead: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Developer on call: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | QA on call: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Operations on call: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Hypercare schedule (24x7 for first week):
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Day shift coverage: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Night shift coverage: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Weekend coverage: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Escalation procedures documented
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | War room setup:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Physical location: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Virtual war room (Teams/Zoom): ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.2 Deployment Planning (Week 9-10) | Daily status meeting scheduled
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Production Readiness Checklist
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | All must-have features implemented
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | All acceptance criteria met
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | All critical bugs resolved
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | All high bugs resolved
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Known issues documented and accepted
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Performance benchmarks met
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Load testing passed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Auto-scaling validated
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Performance under expected load validated
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Security review completed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Penetration testing passed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | All critical/high vulnerabilities resolved
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | All secrets in Key Vault
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Audit logging enabled and tested
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Compliance requirements met
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Data privacy controls implemented
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Regulatory approvals obtained (if applicable)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Compliance documentation complete
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Monitoring and alerting configured
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Dashboards created and tested
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Alert testing completed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Operations runbook complete
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | On-call rotation established
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Incident response plan ready
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Backup and recovery tested
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Architecture documentation complete
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | API documentation complete
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | User documentation complete
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Operations runbook complete
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Deployment guide complete
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | End users trained (>90% coverage)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Support team trained
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Operations team trained
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Training effectiveness validated
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Deployment plan approved
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Rollback plan approved
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Communication plan ready
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Hypercare plan ready
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Change request approved
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Go/No-Go Meeting
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Meeting scheduled: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | All stakeholders invited:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Executive Sponsor
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Product Owner
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Technical Lead
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | DevOps Lead
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Security Lead
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Compliance Lead
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Operations Lead
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Business Stakeholders
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Production readiness checklist reviewed (100% complete)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Risks and mitigations reviewed
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Open issues reviewed and accepted
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Go-Live decision made:
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | GO ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | NO-GO ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | CONDITIONAL GO ☐
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | If GO: Deployment date confirmed: ___________
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Production readiness validated (100%)
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Go-Live approval obtained
WEEKS 9-10: PRODUCTION DEPLOYMENT PREPARATION | 9.3 Production Readiness Review (Week 10) | Deployment date confirmed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | Final Preparations
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | Final Go/No-Go decision reconfirmed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | Deployment team briefing completed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | Production environment health check passed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | Production backup completed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | Rollback plan reviewed with team
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | Communication sent to users (deployment notice)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.1 Pre-Deployment (Week 11, Day 1) | War room ready
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment Day: D-Day
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment date: ___________
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment start time: ___________
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment end time: ___________
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment Steps
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Production environment health check
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | All systems status: GREEN
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment team on standby
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Stakeholders notified (deployment starting)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deploy application to Blue environment
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deploy ML models to Blue endpoints
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deploy data pipelines
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deploy integrations
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Smoke tests on Blue:
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Health check endpoint responding
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Prediction API working
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | UI accessible
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Integrations functional
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Integration tests on Blue: All passing ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Route 10% traffic to Blue
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Monitor for 30 minutes
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Error rate: _____% (target: <0.1%)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Latency P95: _____ ms (target: <100ms)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | No critical issues
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | If stable, route 50% traffic to Blue
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Monitor for 30 minutes
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Error rate: _____% (target: <0.1%)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Latency P95: _____ ms (target: <100ms)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | No critical issues
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | If stable, route 100% traffic to Blue
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Monitor for 1 hour
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Error rate: _____% (target: <0.1%)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Latency P95: _____ ms (target: <100ms)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | No critical issues
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Blue becomes new production (Green)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Old production (Green) kept as rollback option
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Post-deployment smoke tests:
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | User login working
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Prediction working
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Integrations working
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Monitoring active
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Alerts configured
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | End-to-end test scenarios executed: All passing ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Monitoring dashboards reviewed: All healthy ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Stakeholders notified (deployment successful)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Users notified (system available)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment Status
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Deployment completed successfully: Yes ☐ No ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Issues encountered: ___________________________________________
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Rollback executed: Yes ☐ No ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Production deployment completed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | System live and operational
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.2 Deployment Execution (Week 11, Days 2-3) | Hypercare begins
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Hypercare Monitoring (24x7)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | War room active
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Hypercare team on duty
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Daily standup meetings:
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 1 (D+1) standup ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 2 (D+2) standup ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 3 (D+3) standup ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 4 (D+4) standup ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 5 (D+5) standup ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 6 (D+6) standup ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 7 (D+7) standup ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Monitoring & Metrics
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Application availability: _____%
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Average response time: _____ ms
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Error rate: _____%
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Model predictions: _____ per day
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Active users: _____
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | User adoption rate: _____%
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Issue Tracking
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Issues logged: _____
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Critical issues: _____ (all must be resolved immediately)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | High issues: _____ (resolve within 24 hours)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Medium issues: _____ (resolve within 3 days)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Low issues: _____ (scheduled for next release)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | All critical issues resolved: Yes ☐ No ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Daily Status Reports
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 1 report sent ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 2 report sent ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 3 report sent ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 4 report sent ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 5 report sent ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 6 report sent ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Day 7 report sent ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | User Support
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | User questions/issues tracked
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Quick response to user inquiries (<2 hours)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | User satisfaction monitored
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.3 Hypercare (Week 11, Days 4-5; Week 12, Days 1-7) | Additional training provided (if needed)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | System Stability Validation
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | No critical issues in past 48 hours
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Error rate <0.1%
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Performance targets met consistently
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | User adoption trending positively
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Stakeholders satisfied
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Handoff to Operations
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Formal handoff meeting scheduled: ___________
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Handoff meeting completed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Knowledge transfer completed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Operations team confident and ready
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Hypercare officially ends
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Normal support begins
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | On-call rotation activated
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Post-Deployment Review
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Post-deployment review meeting: ___________
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | What went well?
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | What didn't go well?
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | What should we do differently next time?
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Lessons learned documented
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | System stable and performing well
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Hypercare completed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.4 Stabilization (Week 12, Days 1-5) | Operations team managing system
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Success Metrics Review
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Business objectives met: Yes ☐ No ☐ Partially ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Technical objectives met: Yes ☐ No ☐ Partially ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | User adoption target met: _____% (target: ___%)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | User satisfaction score: _____/5 (target: >4/5)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Performance targets met: Yes ☐ No ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | ROI on track: Yes ☐ No ☐
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Project Closure Activities
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Lessons learned session conducted
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Lessons learned documented
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Project closure report completed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Final presentation to stakeholders
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Project artifacts archived
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Team recognition and celebration! 🎉
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Transition to BAU (Business As Usual)
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Support model established
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Enhancement process defined
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Continuous improvement plan
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Product roadmap for future releases
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Project officially closed
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Success validated
WEEKS 11-12: PRODUCTION DEPLOYMENT & STABILIZATION | 11.5 Project Closure (Week 12, Day 5) | Transition to BAU complete
PHASE EXIT CRITERIA |  | ✅ All must-have features implemented and tested
PHASE EXIT CRITERIA |  | ✅ UAT completed and signed off
PHASE EXIT CRITERIA |  | ✅ All training completed (users, support, operations)
PHASE EXIT CRITERIA |  | ✅ All documentation completed and published
PHASE EXIT CRITERIA |  | ✅ Production deployment successful
PHASE EXIT CRITERIA |  | ✅ Hypercare completed (7+ days stable operation)
PHASE EXIT CRITERIA |  | ✅ User adoption >80%
PHASE EXIT CRITERIA |  | ✅ User satisfaction >4/5
PHASE EXIT CRITERIA |  | ✅ Performance targets met
PHASE EXIT CRITERIA |  | ✅ No critical outstanding issues
PHASE EXIT CRITERIA |  | ✅ Operations team managing system
PHASE EXIT CRITERIA |  | ✅ Handoff to BAU complete
PHASE EXIT CRITERIA |  | ✅ Project closure activities complete