## 06 Test Evaluate Phase
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
PHASE GATE: INTEGRATE PHASE COMPLETE |  | Integration phase completed successfully
PHASE GATE: INTEGRATE PHASE COMPLETE |  | All planned integrations implemented and tested
PHASE GATE: INTEGRATE PHASE COMPLETE |  | Integration test cases passed (>95% success rate)
PHASE GATE: INTEGRATE PHASE COMPLETE |  | UAT environment ready with production-like data
PHASE GATE: INTEGRATE PHASE COMPLETE |  | Test team identified and trained
PHASE GATE: INTEGRATE PHASE COMPLETE |  | Test & Evaluate phase kickoff completed
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Master Test Plan Developed
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Document created date: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test scope defined (functional, non-functional, integration, security, performance)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test approach documented (manual, automated, hybrid)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test schedule created with milestones
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Resource allocation plan (testers, environments, tools)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Entry and exit criteria defined for each test phase
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Defect management process documented
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Risk assessment completed
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Approved by: ___________ Date: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test Strategy Document
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Testing methodology defined (Agile, V-Model, etc.)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test levels defined:
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Unit testing (Developer-owned)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Integration testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | System testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | User Acceptance Testing (UAT)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Performance testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Security testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Model validation testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test types documented:
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Functional testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Non-functional testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Regression testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Smoke testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | End-to-end testing
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test automation strategy defined (% automation target: _____%)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Approved by test manager and stakeholders
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test Scope Definition
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | All functional requirements (count: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | All non-functional requirements (count: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | All integrations (count: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | ML model performance validation
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Data quality and accuracy
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Security and compliance
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Performance and scalability
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Usability and accessibility
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Item 1: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Item 2: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Item 3: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test Environment Validation
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | UAT environment URL: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Environment mirrors production (infrastructure, configuration)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test data loaded and validated (volume: _____ records)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test data covers all scenarios (positive, negative, edge cases)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | PII/sensitive data masked or anonymized
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | All integrations connected to test systems
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Monitoring and logging operational
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Environment access granted to all testers
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Environment stability validated (>99% uptime last 7 days)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Master Test Plan (approved)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test Strategy Document (approved)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test Environment ready (validated)
WEEK 1: TEST PREPARATION & PLANNING | 1.1 Test Planning | Test schedule published
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Functional Test Cases Created
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test cases mapped to all functional requirements
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Total functional test cases: _____ (Target: 100% requirement coverage)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test case structure includes:
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test case ID and name
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Preconditions
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test steps (detailed, executable)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Expected results
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Actual results (placeholder)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Pass/Fail status (placeholder)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Positive test cases: _____
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Negative test cases: _____
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Edge case test cases: _____
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test cases reviewed and approved
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Integration Test Cases Created
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test cases for each integration point
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Total integration test cases: _____ (one per integration minimum)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Data flow validation test cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | API contract test cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Error handling test cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Performance test cases (integration latency)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test cases reviewed and approved
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | User Scenario Test Cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | End-to-end user scenarios documented
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Total user scenarios: _____ (Target: 10-20 scenarios)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Scenarios cover all user personas:
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Persona 1: ___________ (scenarios: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Persona 2: ___________ (scenarios: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Persona 3: ___________ (scenarios: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Scenarios cover critical business processes
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Scenarios validated with business stakeholders
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Non-Functional Test Cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Performance test scenarios (load, stress, endurance)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Security test scenarios (authentication, authorization, data protection)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Usability test scenarios (user experience, navigation)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Accessibility test scenarios (WCAG 2.1 AA compliance)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Compatibility test scenarios (browsers, devices, OS)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Disaster recovery test scenarios
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test cases reviewed and approved
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | ML Model Test Cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Model accuracy test cases (precision, recall, F1-score)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Model fairness test cases (bias across demographics)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Model explainability test cases (SHAP, LIME)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Model robustness test cases (adversarial inputs)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Data drift detection test cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Model performance under load
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test cases reviewed by data science team
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test Data Prepared
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test data sets created for each test type
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Positive test data: _____ records
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Negative test data: _____ records
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Edge case test data: _____ records
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Performance test data: _____ records (representative volume)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test data validated for quality and coverage
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test data documented and versioned
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Functional test cases: _____ cases (100% requirement coverage)
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Integration test cases: _____ cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | User scenario test cases: _____ scenarios
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Non-functional test cases: _____ cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | ML model test cases: _____ cases
WEEK 1: TEST PREPARATION & PLANNING | 1.2 Test Case Development | Test data sets prepared and validated
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Test Management Tool Configured
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Tool selected: ___________ (Azure Test Plans, Jira, TestRail, etc.)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Test cases imported/created in tool
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Test cycles/suites organized
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Testers granted access
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Defect workflow configured
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Reporting dashboards configured
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Test Automation Framework
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Automation framework selected: ___________ (Selenium, Playwright, Cypress, etc.)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Framework configured and validated
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Automated test scripts developed (count: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Automation coverage: _____% (Target: 60-80% for regression)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | CI/CD pipeline integration for automated tests
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Automated test execution validated
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Performance Testing Tools
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Tool selected: ___________ (JMeter, Locust, K6, Azure Load Testing, etc.)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Load test scripts developed
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Performance test environment validated
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Baseline performance metrics captured
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Performance monitoring configured
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Security Testing Tools
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Vulnerability scanner configured: ___________ (Burp Suite, OWASP ZAP, etc.)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | SAST tool configured: ___________ (SonarQube, Checkmarx, etc.)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | DAST tool configured: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Penetration testing vendor engaged: ___________ (if applicable)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Security test scenarios prepared
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Accessibility Testing Tools
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Tool selected: ___________ (Axe, WAVE, JAWS, NVDA, etc.)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Accessibility test scenarios prepared
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Screen reader testing planned
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Test management tool operational
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Test automation framework ready (_____ automated tests)
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Performance testing tools configured
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Security testing tools configured
WEEK 1: TEST PREPARATION & PLANNING | 1.3 Test Tools & Infrastructure | Accessibility testing tools ready
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Test Team Assembled
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Test Lead: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Functional Testers: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Technical Testers: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Business/UAT Testers: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Performance Testers: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Security Testers: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Total team size: _____ members
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Tester Training Delivered
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Application overview training completed
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Test tool training completed
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Test case walkthrough completed
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | UAT environment walkthrough completed
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Defect logging process training completed
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | AI/ML concepts training (for model testing)
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Training completion rate: _____% (Target: 100%)
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Business User Training (for UAT)
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | UAT tester identification completed (count: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | UAT roles mapped:
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Business process owner: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Power users: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | End users: ___________
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Application training delivered to UAT testers
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | UAT test scenario walkthrough completed
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | UAT expectations set (timeline, effort, sign-off process)
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Test team onboarded and trained
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | UAT testers identified and trained (count: _____)
WEEK 1: TEST PREPARATION & PLANNING | 1.4 Tester Training & Onboarding | Training materials and recordings available
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | UAT Kickoff Meeting
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Meeting date: ___________
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | All UAT testers present
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | UAT scope and timeline reviewed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Test cases assigned to testers
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Support channels communicated
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Daily sync meetings scheduled
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Functional Testing Execution
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Total test cases: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Test cases executed: _____ (_____%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Test cases passed: _____ (_____%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Test cases failed: _____ (_____%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Test cases blocked: _____ (_____%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Test coverage: _____% (Target: >95%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 1 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 2 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 3 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 4 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 5 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 1 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 2 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 3 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 4 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Day 5 (___/___): _____ tests executed, _____ passed, _____ failed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Requirement Coverage Validation
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | All functional requirements tested
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Requirements traceability matrix updated
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Coverage report generated: _____% (Target: 100%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Gaps identified and addressed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Critical Path Testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | All critical business processes tested
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Critical path 1: ___________ Status: Pass/Fail
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Critical path 2: ___________ Status: Pass/Fail
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Critical path 3: ___________ Status: Pass/Fail
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Critical path 4: ___________ Status: Pass/Fail
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Critical path 5: ___________ Status: Pass/Fail
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | All critical paths passed: Yes/No
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | UAT execution report (daily)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Test coverage report (>95%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.1 UAT Execution - Functional Testing | Critical path validation (100% passed)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | End-to-End Scenario Testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 1: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 2: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 3: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 4: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 5: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 6: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 7: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 8: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 9: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Scenario 10: ___________ ¦ Tester: ___________ ¦ Status: Pass/Fail ¦ Defects: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Business Process Validation
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | All business processes validated with process owners
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Process 1: ___________ ¦ Owner: ___________ ¦ Sign-off: Yes/No
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Process 2: ___________ ¦ Owner: ___________ ¦ Sign-off: Yes/No
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Process 3: ___________ ¦ Owner: ___________ ¦ Sign-off: Yes/No
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Process 4: ___________ ¦ Owner: ___________ ¦ Sign-off: Yes/No
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Process owners confirm solution meets business needs
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | User Experience Testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Navigation and workflow testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | User interface usability testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Response time perception testing (<3 seconds for user actions)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Error message clarity testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Help and documentation testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | User feedback collected and analyzed
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | End-to-end scenario results (>90% passed)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | Business process validation sign-offs
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.2 User Scenario & End-to-End Testing | User experience feedback report
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Usability Testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Usability test sessions conducted: _____ sessions
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Test participants: _____ users (representative of user base)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Usability metrics measured:
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Task completion rate: _____% (Target: >90%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Task completion time: _____ seconds (vs. baseline: _____ seconds)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Error rate: _____% (Target: <10%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | User satisfaction score: _____/5 (Target: >4.0)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Usability issues identified: _____ issues
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Critical usability issues: _____ (must fix before go-live)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Usability report created
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Accessibility Testing (WCAG 2.1 AA)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Tool used: ___________ (Axe, WAVE, Lighthouse)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Pages scanned: _____ pages
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Violations found: _____ (Level A: _____, Level AA: _____, Level AAA: _____)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Critical violations: _____ (Level A/AA - must fix)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Violations fixed: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Re-scan passed: Yes/No
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Keyboard navigation testing (all functionality accessible without mouse)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Screen reader testing (JAWS, NVDA, VoiceOver)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Color contrast testing (minimum 4.5:1 ratio)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Focus management testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Form label and error announcement testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Skip navigation and landmarks testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Alternative text for images testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Video captions and transcripts (if applicable)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | WCAG 2.1 Level A compliance: _____% (Target: 100%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | WCAG 2.1 Level AA compliance: _____% (Target: 100%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Accessibility audit report created
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Accessibility statement published
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Localization Testing (if applicable)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Languages tested: ___________ (e.g., English, Spanish, French)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Translation accuracy verified
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Cultural appropriateness validated
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Date, time, currency formats validated
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Right-to-left language support tested (if applicable)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Character encoding testing
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Usability test report with recommendations
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Accessibility audit report (WCAG 2.1 AA compliance: _____%)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.3 Usability & Accessibility Testing | Localization test results (if applicable)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect Logging Process
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect management tool: ___________ (Azure DevOps, Jira, etc.)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect template includes:
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect ID
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Title and description
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Steps to reproduce
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Expected vs. actual result
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Screenshots/videos
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Environment details
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Severity and priority
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Assigned to (developer)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Status (New, Active, Resolved, Closed)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | All testers trained on defect logging
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect Tracking Metrics (Update Daily)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Total defects logged: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Critical (P1): _____ ¦ Open: _____ ¦ Resolved: _____ ¦ Closed: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | High (P2): _____ ¦ Open: _____ ¦ Resolved: _____ ¦ Closed: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Medium (P3): _____ ¦ Open: _____ ¦ Resolved: _____ ¦ Closed: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Low (P4): _____ ¦ Open: _____ ¦ Resolved: _____ ¦ Closed: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defects open >7 days: _____ (should be minimal)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defects open >14 days: _____ (should be zero for P1/P2)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Average defect resolution time: _____ days
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Functional issues: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | UI/UX issues: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Integration issues: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Performance issues: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Security issues: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Data quality issues: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Documentation issues: _____
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect Triage & Prioritization
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Daily defect triage meetings scheduled
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect severity and priority assigned
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Critical defects escalated immediately
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect resolution tracked and monitored
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Regression testing planned for fixed defects
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Go-Live Blocker Criteria
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Zero critical (P1) defects open (must resolve or downgrade)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Zero high (P2) defects open (must resolve, downgrade, or defer with approval)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Medium (P3) defects: Acceptable with business approval
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Low (P4) defects: Can be deferred to post-go-live
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Current blocker status: _____ P1, _____ P2 (must be 0, 0 for go-live)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect log (all defects tracked)
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Daily defect metrics report
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Defect trend analysis
WEEK 2-3: USER ACCEPTANCE TESTING (UAT) | 2.4 Defect Management | Go-live blocker status report
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration Test Execution
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Total integration test cases: _____
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Test cases passed: _____ (_____%) (Target: >95%)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Test cases failed: _____ (_____%)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integrations tested: _____ of _____ (Target: 100%)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration 1: ___________ ¦ Status: Pass/Fail ¦ Issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration 2: ___________ ¦ Status: Pass/Fail ¦ Issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration 3: ___________ ¦ Status: Pass/Fail ¦ Issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration 4: ___________ ¦ Status: Pass/Fail ¦ Issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration 5: ___________ ¦ Status: Pass/Fail ¦ Issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data Flow Validation
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data flow end-to-end validated for each integration
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data accuracy validated (sample validation: _____% accuracy)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data completeness validated (all expected fields present)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data transformation logic validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data latency validated (within SLA: Yes/No)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data error handling validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API Contract Testing
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API endpoints tested: _____ of _____ (Target: 100%)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API request/response format validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API error responses validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API authentication/authorization validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API rate limiting validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API documentation accuracy validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration Error Handling
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Error scenarios tested for each integration
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Retry logic validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Timeout handling validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Circuit breaker pattern validated (if applicable)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Error notifications/alerts validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Error logging validated
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration test results (>95% pass rate)
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Data flow validation report
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | API test results
WEEK 3-4: TECHNICAL TESTING | 3.1 Integration Testing | Integration issues log
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance Test Planning
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance test scenarios defined
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance SLAs defined:
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Response time: _____ ms (p95)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Throughput: _____ requests/second
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Concurrent users: _____
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Error rate: <_____% (Target: <1%)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | System availability: >_____% (Target: >99.9%)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test data volume: _____ records (production-like volume)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Load profile defined (ramp-up, steady state, ramp-down)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Baseline Performance Testing
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Baseline test executed
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Baseline metrics captured:
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Average response time: _____ ms
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | p95 response time: _____ ms
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | p99 response time: _____ ms
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Throughput: _____ req/sec
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | CPU utilization: _____%
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Memory utilization: _____%
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Database response time: _____ ms
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Baseline report created
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Load Testing
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test type: Load test
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Objective: Validate system handles expected load
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Virtual users: _____ (concurrent)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test duration: _____ minutes
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test executed date: ___________
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Results:
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Average response time: _____ ms (SLA: _____ ms) ¦ Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | p95 response time: _____ ms (SLA: _____ ms) ¦ Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | p99 response time: _____ ms (SLA: _____ ms) ¦ Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Throughput: _____ req/sec (SLA: _____ req/sec) ¦ Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Error rate: _____% (SLA: <1%) ¦ Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Resource utilization: CPU: _____%, Memory: _____%
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Overall result: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Stress Testing
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test type: Stress test
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Objective: Identify breaking point and validate graceful degradation
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Virtual users: _____ (concurrent, exceeding expected load by 150-200%)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test duration: _____ minutes
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test executed date: ___________
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Results:
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Breaking point: _____ concurrent users or _____ req/sec
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | System behavior at stress: Stable/Degraded/Failed
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Recovery time after stress: _____ minutes
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Error rate at stress: _____%
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | System failed gracefully: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Overall result: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Endurance/Soak Testing
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test type: Endurance test
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Objective: Validate system stability over extended period
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Virtual users: _____ (concurrent, 70-80% of max capacity)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test duration: _____ hours (minimum 4-8 hours)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test executed date: ___________
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Results:
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Response time degradation: <10% over time (Pass/Fail)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Memory leaks detected: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Resource leaks detected: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Error rate stable: Yes/No (<1%)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | System remained stable: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Overall result: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Spike Testing
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test type: Spike test
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Objective: Validate system handles sudden load spikes
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Virtual users: _____ to _____ (sudden increase)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Spike duration: _____ minutes
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Test executed date: ___________
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Results:
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | System handled spike: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Response time during spike: _____ ms (acceptable: Yes/No)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Error rate during spike: _____%
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Recovery time after spike: _____ minutes
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Overall result: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Database Performance Testing
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Query performance validated (slow queries identified: _____)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Database connection pooling validated
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Database load testing completed
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Database bottlenecks identified and addressed
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Database performance optimized
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | ML Model Inference Performance
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Model inference latency: _____ ms (SLA: _____ ms) ¦ Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Model throughput: _____ predictions/second
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Model performance under concurrent requests validated
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | GPU/CPU utilization: _____%
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Model performance optimized if needed
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance Optimization
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance bottlenecks identified: _____ issues
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Optimization actions taken:
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Action 1: ___________
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Action 2: ___________
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Action 3: ___________
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Re-testing after optimization completed
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance improvements measured: Before: _____ ms, After: _____ ms
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance test results (all SLAs met: Yes/No)
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Load test report
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Stress test report
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Endurance test report
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance bottleneck analysis
WEEK 3-4: TECHNICAL TESTING | 3.2 Performance Testing | Performance optimization recommendations
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security Test Planning
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security test plan created
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security requirements validated
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Threat model reviewed
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security test scope defined
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Penetration testing vendor engaged (if external): ___________
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Authentication & Authorization Testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | User authentication testing (valid and invalid credentials)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Multi-factor authentication testing (if applicable)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Password policy enforcement testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Session management testing (timeout, hijacking prevention)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Role-based access control (RBAC) testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Privilege escalation testing (attempt unauthorized access)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Authorization bypass testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Results: Pass/Fail ¦ Critical issues: _____ ¦ High issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Data Security Testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Data encryption at rest validated (database, storage)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Data encryption in transit validated (TLS 1.2+)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | PII/sensitive data protection validated (masking, redaction)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Data access logging validated (audit trails)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Data retention and deletion validated
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Backup encryption validated
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Results: Pass/Fail ¦ Issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Input Validation & Injection Testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | SQL injection testing (all inputs validated)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Cross-site scripting (XSS) testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Command injection testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | LDAP injection testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | XML/JSON injection testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | File upload vulnerability testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Results: Pass/Fail ¦ Critical issues: _____ ¦ High issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | API Security Testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | API authentication testing (JWT, OAuth, API keys)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | API authorization testing (endpoint access control)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | API rate limiting testing (DoS prevention)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | API input validation testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | API error message disclosure testing (no sensitive data in errors)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | API versioning and deprecation testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Results: Pass/Fail ¦ Issues: _____
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Application Security Testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Tool used: ___________ (SonarQube, Checkmarx, etc.)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Code scanning completed
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Vulnerabilities found:
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Critical: _____ (must fix all)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | High: _____ (must fix all)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Medium: _____ (fix or accept risk)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Low: _____ (fix or defer)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Vulnerabilities remediated: _____
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Re-scan passed: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Tool used: ___________ (Burp Suite, OWASP ZAP, etc.)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Application scanning completed
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Vulnerabilities found:
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Critical: _____ (must fix all)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | High: _____ (must fix all)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Medium: _____ (fix or accept risk)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Low: _____ (fix or defer)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Vulnerabilities remediated: _____
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Re-scan passed: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Penetration Testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Penetration test conducted by: ___________ (internal/external)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Test date: ___________
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Test scope: Web application, APIs, infrastructure, network
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Findings:
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Critical: _____ (must fix before go-live)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | High: _____ (must fix before go-live)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Medium: _____ (fix or accept risk with approval)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Low: _____ (defer to post-go-live)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Remediation completed: _____% (Target: 100% critical/high)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Re-test passed: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Penetration test report received
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Compliance Testing
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | GDPR compliance validated (data protection, privacy, consent)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Industry-specific compliance validated (HIPAA, PCI-DSS, etc.): ___________
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Data residency requirements validated
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Audit logging and monitoring validated
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Incident response procedures validated
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Compliance gaps identified: _____ (must address before go-live)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security Go-Live Criteria
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Zero critical security vulnerabilities
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Zero high security vulnerabilities (or approved exceptions)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | All authentication and authorization controls working
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | All data encryption controls working
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security monitoring and alerting operational
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Incident response plan in place
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security sign-off obtained: Yes/No by: ___________
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security test results (critical/high issues: 0)
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | SAST report
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | DAST report
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Penetration test report
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Compliance validation report
WEEK 3-4: TECHNICAL TESTING | 3.3 Security Testing | Security sign-off certificate
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model Performance Testing
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Accuracy: _____% (Target: >_____%)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Precision: _____% (Target: >_____%)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Recall: _____% (Target: >_____%)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | F1-Score: _____ (Target: >_____)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | AUC-ROC: _____ (Target: >_____)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Confusion matrix analyzed
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Overall performance: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | MAE (Mean Absolute Error): _____ (Target: <_____)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | RMSE (Root Mean Squared Error): _____ (Target: <_____)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | R² Score: _____ (Target: >_____)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Overall performance: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Metric 1: ___________: _____ (Target: _____)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Metric 2: ___________: _____ (Target: _____)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Overall performance: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model Fairness & Bias Testing
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Fairness metrics calculated across demographic groups:
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Group 1 (e.g., Gender: Male): Accuracy: _____%, Precision: _____%, Recall: _____%
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Group 2 (e.g., Gender: Female): Accuracy: _____%, Precision: _____%, Recall: _____%
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Demographic parity difference: _____ (Target: <0.1)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Equal opportunity difference: _____ (Target: <0.1)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Protected attributes tested: ___________
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Bias identified: Yes/No ¦ Details: ___________
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Bias mitigation actions (if needed):
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Action 1: ___________
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Action 2: ___________
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Re-test after mitigation: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Fairness validation: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model Explainability Testing
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Explainability method used: ___________ (SHAP, LIME, feature importance, etc.)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Feature importance analysis completed
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Top 10 features identified and validated with business
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model predictions explainable: Yes/No
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Explanation accuracy validated with business users
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Explanation quality: Good/Acceptable/Poor
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Explainability validation: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model Robustness Testing
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Adversarial input testing (model resilience to malicious inputs)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Edge case testing (rare or unusual inputs)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Out-of-distribution input testing
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model stability under varied inputs validated
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model failure modes identified and documented
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Robustness validation: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Data Quality & Drift Testing
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Training data quality validated
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Inference data quality validated
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Data drift detection configured
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Data drift thresholds set: _____
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Data drift monitoring tested
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Data quality monitoring alerts configured
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Data quality validation: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model Monitoring & Alerting
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model performance monitoring configured (accuracy, latency, throughput)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model drift detection configured (concept drift, data drift)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Anomaly detection configured
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Alerting thresholds set:
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Accuracy drop >_____% triggers alert
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Latency >_____ ms triggers alert
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Error rate >_____% triggers alert
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Alert recipients configured
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Monitoring dashboards created
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Monitoring and alerting tested
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model Retraining Validation
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Retraining process documented
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Retraining triggers defined (schedule, performance drop, data drift)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Retraining tested (dry-run completed)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model versioning validated
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model rollback procedure tested
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Retraining process: Pass/Fail
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model performance validation report (meets targets: Yes/No)
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Fairness and bias test report
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Explainability validation report
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Robustness test results
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Data quality monitoring configuration
WEEK 3-4: TECHNICAL TESTING | 3.4 ML Model Validation Testing | Model monitoring dashboards operational
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Regression Test Planning
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Regression test scope defined (all areas impacted by defect fixes)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Regression test cases selected: _____ cases
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Regression test schedule created
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Automated regression tests identified: _____ of _____ (_____% automation)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Regression Test Execution
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Total regression test cases: _____
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Test cases passed: _____ (_____%) (Target: >95%)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Test cases failed: _____ (_____%)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | New defects found: _____ (should be minimal)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Critical areas re-tested:
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Core functionality: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Critical integrations: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | ML model predictions: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Security controls: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Regression test result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Automated Regression Test Execution
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Automated tests executed: _____ of _____ automated tests
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Automation pass rate: _____% (Target: >98%)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Automation execution time: _____ minutes
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Failed automated tests investigated and resolved
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | CI/CD pipeline validated with automated tests
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Regression test results (>95% pass rate)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | Automated test execution report
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.1 Regression Testing | New defects log (minimal expected)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Smoke Test Planning
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Smoke test scenarios defined (critical happy path scenarios)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Total smoke test cases: _____ (typically 20-30 critical scenarios)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Smoke test duration: _____ minutes (should be <30 min for quick validation)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Smoke Test Execution (Final)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Test environment: Production (or production-equivalent)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Test date: ___________
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Smoke test scenarios:
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 1: User login ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 2: Core functionality 1 ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 3: Core functionality 2 ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 4: Core functionality 3 ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 5: ML model prediction ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 6: Integration 1 ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 7: Integration 2 ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 8: Data processing ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 9: Reporting/dashboard ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Scenario 10: User logout ¦ Result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Overall smoke test result: Pass/Fail (must be 100% pass for go-live)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Smoke test results (100% pass required)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.2 Smoke Testing (Final Pre-Go-Live) | Go-live readiness confirmation
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR Test Planning
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR test scenarios defined
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR test schedule created
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | RTO (Recovery Time Objective) target: _____ hours
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | RPO (Recovery Point Objective) target: _____ hours
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR test team assembled
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Backup & Restore Testing
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Backup process validated (automated backups running)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Backup frequency: ___________ (daily, hourly, continuous)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Backup restoration tested
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Restore time: _____ hours (meets RTO: Yes/No)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Data loss: _____ hours of data (meets RPO: Yes/No)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Backup integrity validated (data complete and accurate)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Backup test result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Failover Testing
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Failover scenario tested: ___________
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Failover executed date: ___________
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Failover time: _____ minutes (meets RTO: Yes/No)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | System availability during failover: _____% (target: >99.9%)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Data loss during failover: _____ (meets RPO: Yes/No)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Failback tested (return to primary)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Failover test result: Pass/Fail
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR Documentation
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR runbook created and validated
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR roles and responsibilities documented
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR escalation procedures documented
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR communication plan documented
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR test report created
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR test results (RTO/RPO met: Yes/No)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Backup and restore validation report
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | Failover test report
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.3 Disaster Recovery Testing | DR runbook (validated)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Final UAT Review
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | All UAT test cases completed: _____% (Target: 100%)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | All critical test scenarios passed
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | All critical defects resolved (P1: 0, P2: 0)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Medium/low defects reviewed and accepted
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | User acceptance feedback collected
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Business stakeholder concerns addressed
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | UAT Sign-Off
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Business Sponsor: ___________ ¦ Date: ___________ ¦ Sign-off: Yes/No
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Business Process Owner 1: ___________ ¦ Date: ___________ ¦ Sign-off: Yes/No
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Business Process Owner 2: ___________ ¦ Date: ___________ ¦ Sign-off: Yes/No
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | IT Director: ___________ ¦ Date: ___________ ¦ Sign-off: Yes/No
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Security Lead: ___________ ¦ Date: ___________ ¦ Sign-off: Yes/No
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Compliance Lead: ___________ ¦ Date: ___________ ¦ Sign-off: Yes/No
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Go-Live Readiness Assessment
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Functional Testing: _____/10 (all requirements tested and passed)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Integration Testing: _____/10 (all integrations working)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Performance Testing: _____/10 (all SLAs met)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Security Testing: _____/10 (no critical/high vulnerabilities)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | UAT Completion: _____/10 (all scenarios tested, sign-off obtained)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Defect Status: _____/10 (zero P1/P2 open)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Documentation: _____/10 (all docs complete)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Training: _____/10 (>90% users trained)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Support Readiness: _____/10 (helpdesk ready)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | DR Testing: _____/10 (DR validated)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Go-Live Approval
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Change Management Approval obtained: Yes/No ¦ Date: ___________
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Steering Committee Approval obtained: Yes/No ¦ Date: ___________
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Executive Sponsor Approval obtained: Yes/No ¦ Date: ___________
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Go-Live Date Set: ___________ (confirm with all stakeholders)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | UAT sign-off certificate (all stakeholders signed)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Go-live readiness assessment report (score: _____/100)
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Go-live approval certificate
WEEK 4-5: REGRESSION & FINAL VALIDATION | 4.4 UAT Sign-Off & Go-Live Readiness | Go-live date confirmed: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Test Metrics Summary
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Total test cases created: _____
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Total test cases executed: _____ (_____%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Total test cases passed: _____ (_____%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Total test cases failed: _____ (_____%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Test coverage: _____% (Target: >95%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Pass rate: _____% (Target: >95%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Functional testing: _____ cases, _____% passed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Integration testing: _____ cases, _____% passed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Performance testing: _____ scenarios, Pass/Fail
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Security testing: _____ scenarios, Pass/Fail
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | UAT: _____ scenarios, _____% passed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Accessibility testing: Pass/Fail (WCAG 2.1 AA: _____%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | ML model validation: Pass/Fail
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Total defects logged: _____
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Defects resolved: _____ (_____%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Defects closed: _____ (_____%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Open defects remaining: _____ (P1: _____, P2: _____, P3: _____, P4: _____)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Defect density: _____ defects per 100 test cases
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Critical defects: _____ (Target: 0 open)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | High defects: _____ (Target: 0 open)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Defect resolution time (average): _____ days
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Defect reopened rate: _____% (Target: <5%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Test automation coverage: _____%
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Test Summary Report Creation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Executive summary created
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Test approach and scope documented
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Test results summarized by type
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Defect analysis and trends documented
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Quality assessment and risks documented
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Recommendations for post-go-live documented
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Lessons learned captured
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Report reviewed and approved
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Comprehensive Test Summary Report
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Test metrics dashboard
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.1 Test Summary Reporting | Quality assessment certificate
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Known Issues Register
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Issue 1: ___________ ¦ Priority: _____ ¦ Plan: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Issue 2: ___________ ¦ Priority: _____ ¦ Plan: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Issue 3: ___________ ¦ Priority: _____ ¦ Plan: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Issue 4: ___________ ¦ Priority: _____ ¦ Plan: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Issue 5: ___________ ¦ Priority: _____ ¦ Plan: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Impact on go-live: Low / Medium / High
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Mitigation plan for each issue documented
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Workarounds documented (if applicable)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Target resolution timeline: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Risk Log for Test Phase
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Risk 1: ___________ ¦ Impact: _____ ¦ Probability: _____ ¦ Mitigation: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Risk 2: ___________ ¦ Impact: _____ ¦ Probability: _____ ¦ Mitigation: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Risk 3: ___________ ¦ Impact: _____ ¦ Probability: _____ ¦ Mitigation: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | All risks reviewed with steering committee
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | High risks escalated and managed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Known issues register
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Risk log with mitigations
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.2 Known Issues & Risk Log | Post-go-live issue resolution plan
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Test Documentation Complete
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Master test plan (final version)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Test strategy document
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | All test cases (functional, integration, performance, security, UAT)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Test execution reports (by test type)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Defect logs and resolution records
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Test summary report
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | UAT sign-off certificates
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Go-live readiness assessment
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Known issues register
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | User Documentation Validation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | User guides validated with UAT testers
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Admin guides validated with IT team
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | FAQ updated based on UAT feedback
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Training materials validated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Help content validated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Documentation errors corrected
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Technical Documentation Validation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Architecture documentation updated (any changes during testing)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | API documentation validated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Integration documentation validated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Runbooks and SOPs validated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | DR documentation validated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Monitoring and alerting documentation complete
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Complete test documentation package
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Validated user documentation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.3 Documentation Finalization | Validated technical documentation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Handoff to Deployment Team
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Deployment team briefed on test results
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Known issues communicated to deployment team
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Go-live readiness confirmed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Deployment prerequisites validated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Deployment runbook reviewed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Rollback plan reviewed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Hypercare plan reviewed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support Team Preparation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support team briefed on application and known issues
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support runbooks provided
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Escalation procedures communicated
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support ticketing system configured
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support team access to monitoring dashboards
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support team ready for hypercare: Yes/No
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Training Completion Validation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | User training completion: _____% (Target: >90%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Admin training completion: _____% (Target: 100%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support team training completion: _____% (Target: 100%)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Training feedback collected and addressed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Refresher training scheduled (if needed)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Phase Gate Review
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Phase gate review meeting scheduled: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | All phase deliverables completed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | All exit criteria met (see below)
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Steering committee review completed
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Approval to proceed to Prepare & Deploy: Yes/No
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Approved by: ___________ Date: ___________
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Handoff package to Prepare & Deploy team
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Support team readiness confirmation
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Training completion report
WEEK 5-6: TEST CLOSURE & TRANSITION | 5.4 Transition to Prepare & Deploy Phase | Phase gate approval
PHASE GATE: TEST & EVALUATE COMPLETE |  | Testing Complete
PHASE GATE: TEST & EVALUATE COMPLETE |  | All planned test cases executed (>95%)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Test coverage >95% of requirements
PHASE GATE: TEST & EVALUATE COMPLETE |  | Pass rate >95% for all test types
PHASE GATE: TEST & EVALUATE COMPLETE |  | UAT completed and signed off
PHASE GATE: TEST & EVALUATE COMPLETE |  | Quality Metrics Met
PHASE GATE: TEST & EVALUATE COMPLETE |  | Zero critical (P1) defects open
PHASE GATE: TEST & EVALUATE COMPLETE |  | Zero high (P2) defects open (or approved exceptions)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Medium/low defects reviewed and accepted
PHASE GATE: TEST & EVALUATE COMPLETE |  | Test summary report approved
PHASE GATE: TEST & EVALUATE COMPLETE |  | Performance Validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | Load testing passed (all SLAs met)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Stress testing passed
PHASE GATE: TEST & EVALUATE COMPLETE |  | Endurance testing passed
PHASE GATE: TEST & EVALUATE COMPLETE |  | Performance benchmarks documented
PHASE GATE: TEST & EVALUATE COMPLETE |  | Security Validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | Zero critical security vulnerabilities
PHASE GATE: TEST & EVALUATE COMPLETE |  | Zero high security vulnerabilities (or approved exceptions)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Penetration testing passed
PHASE GATE: TEST & EVALUATE COMPLETE |  | Security sign-off obtained
PHASE GATE: TEST & EVALUATE COMPLETE |  | ML Model Validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | Model performance meets success criteria
PHASE GATE: TEST & EVALUATE COMPLETE |  | Model fairness validated (no significant bias)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Model explainability validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | Model monitoring operational
PHASE GATE: TEST & EVALUATE COMPLETE |  | Integration Validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | All integrations tested and working (>95% success rate)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Data flows validated end-to-end
PHASE GATE: TEST & EVALUATE COMPLETE |  | Integration error handling validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | Accessibility & Compliance
PHASE GATE: TEST & EVALUATE COMPLETE |  | WCAG 2.1 Level AA compliance achieved (100%)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Compliance requirements met (GDPR, industry-specific)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Accessibility sign-off obtained
PHASE GATE: TEST & EVALUATE COMPLETE |  | Go-Live Readiness
PHASE GATE: TEST & EVALUATE COMPLETE |  | Go-live readiness score ≥85/100
PHASE GATE: TEST & EVALUATE COMPLETE |  | UAT sign-off obtained from all stakeholders
PHASE GATE: TEST & EVALUATE COMPLETE |  | Change management approval obtained
PHASE GATE: TEST & EVALUATE COMPLETE |  | Steering committee approval obtained
PHASE GATE: TEST & EVALUATE COMPLETE |  | Go-live date confirmed
PHASE GATE: TEST & EVALUATE COMPLETE |  | Documentation & Training
PHASE GATE: TEST & EVALUATE COMPLETE |  | All documentation complete and validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | User training completion >90%
PHASE GATE: TEST & EVALUATE COMPLETE |  | Support team training complete
PHASE GATE: TEST & EVALUATE COMPLETE |  | Runbooks and SOPs validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | Disaster Recovery
PHASE GATE: TEST & EVALUATE COMPLETE |  | DR testing passed (RTO/RPO met)
PHASE GATE: TEST & EVALUATE COMPLETE |  | Backup and restore validated
PHASE GATE: TEST & EVALUATE COMPLETE |  | Failover tested successfully