## 07 Prepare Deploy Phase
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | Test & Evaluate phase completed successfully
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | UAT sign-off obtained from all stakeholders
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | Zero P1/P2 defects open
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | All performance testing passed (SLAs met)
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | Security testing passed (no critical/high vulnerabilities)
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | ML model validation passed
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | Go-live readiness assessment ≥85/100
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | Test summary report approved
PHASE GATE: TEST & EVALUATE PHASE COMPLETE |  | Production environment ready
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Production Environment Final Check
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Production subscription/environment URL: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | All infrastructure deployed and configured
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Compute resources: _____ (VMs, App Services, AKS, etc.)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Storage resources: _____ (Blob, ADLS, SQL, Cosmos, etc.)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Networking configured (VNets, NSGs, firewalls, load balancers)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Security controls operational (Key Vault, Managed Identity, Azure AD)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Monitoring configured (Application Insights, Log Analytics)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Backup configured (automated backups scheduled)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Disaster recovery configured (geo-redundancy, failover)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Environment stability: >99% uptime last 7 days
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Environment sign-off: ___________ Date: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Production Configuration Validation
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Application settings configured for production
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Connection strings configured (all integrations)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | API keys and secrets stored in Key Vault
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Environment variables set correctly
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Feature flags configured
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Scaling policies configured (auto-scaling rules)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Resource quotas and limits configured
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Configuration validated against checklist
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Production Access & Security
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Production access granted to deployment team
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Role-based access control (RBAC) configured
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Just-in-time (JIT) access configured for privileged operations
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Multi-factor authentication (MFA) enforced
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Audit logging enabled for all production access
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Security baselines validated
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Compliance requirements validated
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data Migration Readiness (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data migration plan created
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data migration scripts developed and tested
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data validation queries prepared
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data reconciliation process defined
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data cutover window scheduled: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Rollback data procedures documented
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data migration dry-run completed in UAT: Pass/Fail
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Production environment validated and ready
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Configuration checklist completed
WEEK 1: DEPLOYMENT PREPARATION | 1.1 Production Environment Validation | Data migration plan (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment Strategy Selection
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment approach: ☐ Big Bang ☐ Phased ☐ Blue-Green ☐ Canary
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment window: ___________ (date and time)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment duration estimate: _____ hours
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Business impact assessment completed
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | User downtime (if any): _____ hours
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Blackout period scheduled (if needed): ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment approach approved by: ___________ Date: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Detailed Deployment Plan
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Document created date: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment scope defined (what's being deployed)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment sequence documented (step-by-step)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment dependencies identified
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment team roles assigned:
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment Lead: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Technical Lead: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Database Administrator: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Network Engineer: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Security Engineer: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Test Lead: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Business SME: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Communication plan for deployment day
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Go/No-Go decision criteria defined
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment plan reviewed and approved
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment Runbook Development
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Step-by-step deployment procedures documented
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Pre-deployment checklist included
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment commands/scripts documented
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Configuration changes documented
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Database migration scripts included (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Post-deployment validation steps included
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Smoke test scenarios included
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Expected duration for each step documented
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Screenshots/examples included where helpful
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Runbook reviewed by deployment team
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Runbook tested in UAT environment: Pass/Fail
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Cutover Plan
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Cutover activities sequenced with timing
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | T-minus timeline created (T-7 days to T+7 days)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Cutover checklist created
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Communication points identified
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Fallback points identified
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | User blackout period (if needed) communicated
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Legacy system decommission plan (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Data migration timing included (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Cutover plan approved by stakeholders
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback Plan
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback triggers defined (conditions requiring rollback)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback procedures documented (step-by-step)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback decision makers identified
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback timing estimates: _____ hours
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Data rollback procedures included (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Communication plan for rollback scenario
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback tested in UAT environment: Pass/Fail
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback plan approved
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment plan (approved)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Deployment runbook (tested)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Cutover plan (approved)
WEEK 1: DEPLOYMENT PREPARATION | 1.2 Deployment Planning | Rollback plan (tested and approved)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change Request Submission
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change request ID: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change request submitted date: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change type: ☐ Standard ☐ Normal ☐ Emergency
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change request includes:
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Detailed description of change
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Business justification
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Risk assessment
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Impact assessment (systems, users, business processes)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Deployment plan
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Rollback plan
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Test results
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | UAT sign-off
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change request submitted to CAB (Change Advisory Board)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change Approval
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | CAB review date: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Questions/concerns addressed
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Change approved by: ___________ Date: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Deployment window approved: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Conditions of approval (if any): ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Stakeholder Communication
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Deployment notification sent to all stakeholders
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Notification includes:
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Deployment date and time
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Expected duration
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Impact on users (downtime, if any)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | What's being deployed (features)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Support contact information
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Notification sent to:
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Executive sponsors
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Business users (all)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | IT operations
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Support team
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | External partners (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Reminder notifications scheduled (T-3 days, T-1 day, T-day)
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Approved change request
WEEK 1: DEPLOYMENT PREPARATION | 1.3 Change Management & Approvals | Stakeholder communication sent
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Dry-Run Deployment
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Dry-run scheduled date: ___________
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Dry-run environment: UAT
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Deployment team assembled
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Deployment runbook followed step-by-step
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Timing for each step captured:
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Pre-deployment checks: _____ minutes
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Application deployment: _____ minutes
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Database migration: _____ minutes (if applicable)
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Configuration updates: _____ minutes
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Post-deployment validation: _____ minutes
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Smoke testing: _____ minutes
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Total time: _____ minutes (vs. estimate: _____ minutes)
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Issues identified during dry-run: _____
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | All issues resolved
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Dry-run result: Pass/Fail
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Lessons from Rehearsal
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Runbook updated based on dry-run
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Timing estimates refined
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Missing steps added
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Unclear steps clarified
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Team roles refined if needed
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Deployment plan updated
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Rollback Testing
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Rollback tested in UAT environment
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Rollback time: _____ minutes
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Rollback successful: Yes/No
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Data integrity verified post-rollback
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Rollback plan updated based on test
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Dry-run deployment completed successfully
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Updated deployment runbook
WEEK 1: DEPLOYMENT PREPARATION | 1.4 Deployment Rehearsal | Validated rollback plan
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | User Training Materials
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | User guide completed and reviewed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Quick start guide created
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Training presentation/slides finalized
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Training videos recorded (count: _____)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Hands-on exercises/labs prepared
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | FAQs document created (common questions answered)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Cheat sheets/job aids created
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Training materials reviewed by SMEs
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Training materials approved by: ___________ Date: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Administrator Training Materials
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Admin guide completed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Configuration guide created
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Operations runbook finalized
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Troubleshooting guide created
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Admin training presentation prepared
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Admin hands-on labs prepared
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Admin materials reviewed and approved
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Support Team Materials
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Support runbook created
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Common issues and resolutions documented
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Escalation procedures documented
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Knowledge base articles created (count: _____)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Support scripts prepared
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Support materials reviewed and approved
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Training Materials Distribution
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Materials uploaded to training platform/portal
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Materials shared with all trainees
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Access to training environment granted
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Training schedule communicated
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Complete training materials package
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.1 Training Material Finalization | Materials distributed to all trainees
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training Sessions Scheduled
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training approach: ☐ In-person ☐ Virtual ☐ Hybrid ☐ Self-paced
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Number of training sessions: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training environment URL: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training data prepared and loaded
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training sessions scheduled:
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Session 1: Date: ___________ Time: ___________ Attendees: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Session 2: Date: ___________ Time: ___________ Attendees: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Session 3: Date: ___________ Time: ___________ Attendees: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Session 4: Date: ___________ Time: ___________ Attendees: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Session 5: Date: ___________ Time: ___________ Attendees: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Calendar invites sent to all trainees
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Trainers confirmed and prepared
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training Delivery
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Date delivered: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Attendance: _____ of _____ (_____%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training evaluation score: _____/5
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Issues/questions logged: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Follow-up actions: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Date delivered: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Attendance: _____ of _____ (_____%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training evaluation score: _____/5
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Issues/questions logged: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Follow-up actions: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Date delivered: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Attendance: _____ of _____ (_____%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training evaluation score: _____/5
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Issues/questions logged: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Follow-up actions: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Date delivered: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Attendance: _____ of _____ (_____%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training evaluation score: _____/5
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Issues/questions logged: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Follow-up actions: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Date delivered: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Attendance: _____ of _____ (_____%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training evaluation score: _____/5
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Issues/questions logged: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Follow-up actions: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training Completion Tracking
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Total users requiring training: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Users trained: _____ (_____%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training completion target: >90% (met: Yes/No)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Makeup sessions scheduled for missed trainees: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training certificates issued: _____
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training attendance records maintained
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training Effectiveness
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Average training evaluation score: _____/5 (Target: >4.0)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training feedback analyzed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Common questions/issues identified and addressed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Follow-up training sessions scheduled (if needed)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Refresher training plan created
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | User training delivered (>90% completion)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training attendance records
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.2 User Training Delivery | Training evaluation results
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Administrator Training
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Admin training session date: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Attendance: _____ of _____ admins (Target: 100%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Topics covered:
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | System configuration and settings
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | User management and access control
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Monitoring and alerting
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Backup and recovery procedures
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Performance optimization
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Troubleshooting common issues
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Patch management and updates
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Hands-on practice completed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Admin knowledge validated (quiz/assessment)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Admin training evaluation: _____/5
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Admin training completion certificates issued
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Support Team Training
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Support team training date: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Attendance: _____ of _____ support staff (Target: 100%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Topics covered:
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Application functionality overview
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Common user issues and resolutions
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Ticketing and escalation procedures
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Access to support tools and systems
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Knowledge base usage
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | When to escalate to L2/L3 support
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Role-play exercises completed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Support team knowledge validated
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Support team training evaluation: _____/5
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Support team ready for hypercare: Yes/No
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Technical Team Handover
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Handover session scheduled: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Development team to operations team handover completed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Architecture review session delivered
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Codebase walkthrough delivered
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Operations runbook reviewed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Known issues communicated
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Technical documentation reviewed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | On-call rotation established
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Operations team sign-off: ___________ Date: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Administrator training completed (100%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Support team training completed (100%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.3 Administrator & Support Training | Technical handover completed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Change Champion Network
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Change champions identified: _____ champions
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Champions represent all user groups/departments
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Champions training delivered
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Champions briefed on their role
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Champions communication toolkit provided
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Champions activated and engaged
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User Communication Campaign
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Go-live communication sent (T-2 weeks)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | What's changing and why
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Benefits to users
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Training opportunities
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Go-live date and impact
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Where to get help
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Reminder communication sent (T-1 week)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Final reminder sent (T-2 days)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Communication channels used:
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Email to all users
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Intranet announcement
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Team meetings/town halls
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Posters/flyers (physical locations)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Yammer/Teams channels
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Communication effectiveness measured (open rate: _____%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Change Readiness Assessment
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User sentiment surveyed: _____% positive
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Training completion: _____% (Target: >90%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Change champion engagement: Good/Fair/Poor
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Resistance identified: Low/Medium/High
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Mitigation actions for resistance: ___________
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Overall change readiness: Ready/At Risk/Not Ready
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User Onboarding
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User accounts created: _____ of _____ (100%)
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User roles and permissions assigned
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User access tested and validated
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Welcome emails sent to all users
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User onboarding guide distributed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User onboarding complete
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Change champion network activated
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Communication campaign executed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | Change readiness assessment completed
WEEK 2: TRAINING & CHANGE MANAGEMENT | 2.4 Change Management Activities | User accounts provisioned
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Production Smoke Test (in production, pre-go-live)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Application deployed to production: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Smoke test date: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Smoke test scenarios executed:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | User login/logout: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Core function 1: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Core function 2: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Core function 3: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | ML model prediction: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration 1: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration 2: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Reporting/dashboard: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Overall smoke test result: Pass/Fail (must be 100% pass)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Issues found: _____ (must be resolved before go-live)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Performance Validation in Production
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Production performance test executed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Response times validated: Avg: _____ ms (Target: _____ ms) Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Throughput validated: _____ req/sec (Target: _____ req/sec) Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Resource utilization validated: CPU: _____% Memory: _____%
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Performance meets SLAs: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Security Final Validation
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Production security scan completed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Vulnerabilities found: Critical: _____ High: _____ (must be 0, 0)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Security controls validated:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Authentication working
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Authorization working
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Encryption at rest validated
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Encryption in transit validated (TLS)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Audit logging working
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Security monitoring active
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Security sign-off: ___________ Date: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration Validation
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | All integrations tested in production:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration 1: ___________ Status: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration 2: ___________ Status: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration 3: ___________ Status: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration 4: ___________ Status: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration 5: ___________ Status: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Data flows validated end-to-end
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Error handling tested
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration monitoring active
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Production smoke test passed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Performance validation passed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Security validation passed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.1 Final Pre-Deployment Validation | Integration validation passed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Monitoring Configuration
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Application Insights configured and collecting data
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Log Analytics workspace configured
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Custom metrics configured:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Business metrics: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Technical metrics: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Model metrics: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Monitoring dashboards created:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Executive dashboard (business metrics)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Operations dashboard (system health)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Model performance dashboard
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | User activity dashboard
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Dashboard access granted to stakeholders
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Alerting Configuration
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Alert rules configured:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Application errors (threshold: _____)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Performance degradation (threshold: _____)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Model performance drop (threshold: _____)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Integration failures (threshold: _____)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Security incidents (threshold: _____)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Resource exhaustion (threshold: _____)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Alert recipients configured (email, SMS, Teams)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Alert escalation paths defined
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | On-call schedule configured
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Alerts tested and validated
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Support Infrastructure Setup
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Helpdesk/ticketing system configured
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Support email/phone number active: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Support portal/knowledge base accessible: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Support ticket categories defined
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | SLAs defined for each ticket priority
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Escalation procedures documented
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Support team access to systems validated
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Support team schedule created (24/7 for hypercare)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Backup Validation
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Automated backups configured
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Backup frequency: ___________ (hourly, daily, etc.)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Backup retention: _____ days
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Backup restoration tested: Success/Failure
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Backup restoration time: _____ hours (meets RTO: Yes/No)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Backup monitoring and alerting configured
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Monitoring dashboards operational
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Alerting configured and tested
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Support infrastructure ready
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.2 Monitoring & Support Infrastructure | Backup validated
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Pre-Migration Validation
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data migration scripts validated in UAT
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data volume to migrate: _____ records
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Estimated migration time: _____ hours
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Migration window scheduled: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Legacy system read-only mode scheduled
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Rollback data procedures ready
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data Migration Execution
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Migration start time: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Legacy system set to read-only: Yes/No Time: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data extraction completed: Yes/No Time: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data transformation completed: Yes/No Time: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data loading completed: Yes/No Time: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Migration end time: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Actual migration time: _____ hours (vs. estimate: _____ hours)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data Validation
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Record count validation:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Source records: _____
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Migrated records: _____
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Match: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data quality validation:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Completeness check: _____% (Target: 100%)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Accuracy check: _____% (Target: 100%)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data integrity check: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Business validation with SMEs: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Critical data spot-checked: Pass/Fail
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data migration result: Success/Failure
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Post-Migration
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Legacy system decommissioned/archived (if planned)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data migration report created
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data migration lessons learned documented
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data migration sign-off: ___________ Date: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data migration completed successfully
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data validation passed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.3 Data Migration Execution (if applicable) | Data migration report
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Go/No-Go Meeting Preparation
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Meeting scheduled: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Decision makers confirmed:
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Executive Sponsor: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Business Sponsor: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | IT Director: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Project Manager: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Technical Lead: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Security Lead: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Go-live readiness report prepared
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | All phase gate criteria validated
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Risk assessment updated
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Open issues list prepared
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Go-Live Readiness Checklist
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | All features complete and tested: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | UAT sign-off obtained: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Smoke testing passed in production: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | No critical defects open: Yes/No (P1: _____, P2: _____)
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Production environment ready: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Performance validation passed: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Security validation passed: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Integrations validated: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Monitoring operational: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Backups configured and tested: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Deployment plan approved: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Rollback plan tested: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Support team trained and ready: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Helpdesk operational: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | On-call schedule established: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | User training completed (>90%): Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Change management activities complete: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Communication campaign executed: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | User accounts provisioned: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Business stakeholders ready: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Change request approved: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Deployment window approved: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Risk mitigation plans in place: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Escalation procedures defined: Yes/No
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Go/No-Go Decision
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Meeting date: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Readiness assessment presented
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Questions and concerns addressed
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Risks reviewed and accepted
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | DECISION: ☐ GO ☐ CONDITIONAL GO ☐ NO-GO
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Decision rationale: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Approved by: ___________ Date: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | If CONDITIONAL GO, conditions: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | If NO-GO, blockers: ___________
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Go/No-Go decision documented
WEEK 3: PRE-DEPLOYMENT FINALIZATION | 3.4 Go/No-Go Decision Meeting | Decision communicated to all stakeholders
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | T-2 Days
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Final deployment team briefing
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | All team members confirmed available
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | War room prepared (physical or virtual)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Contact lists validated
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Emergency escalation paths confirmed
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Final go-live communication sent to all users
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | T-1 Day
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Production environment health check: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | All systems operational: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | No unplanned outages: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Deployment runbook final review
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Deployment team ready: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Support team ready: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Final go/no-go confirmation call
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Decision: GO / NO-GO
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | T-Day Morning (Deployment Day)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Deployment team assembled
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | War room active
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Pre-deployment checklist completed
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Final system health check: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Deployment kickoff: Time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Deployment team ready
WEEK 4: DEPLOYMENT & GO-LIVE | 4.1 Final Pre-Deployment Activities | Final go-live confirmation
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Deployment Execution
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Step 1: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Start time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | End time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Status: Success/Failure
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Issues: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Step 2: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Start time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | End time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Status: Success/Failure
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Issues: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Step 3: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Start time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | End time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Status: Success/Failure
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Issues: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Step 4: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Start time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | End time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Status: Success/Failure
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Issues: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Step 5: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Start time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | End time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Status: Success/Failure
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Issues: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Deployment start time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Deployment end time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Total deployment time: _____ hours (vs. estimate: _____ hours)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Deployment result: Success/Failure
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Issues encountered: _____ (all resolved: Yes/No)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Application deployed to production
WEEK 4: DEPLOYMENT & GO-LIVE | 4.2 Production Deployment Execution | Deployment log completed
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Immediate Smoke Testing
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Smoke test start time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Critical scenarios tested:
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | User authentication: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Core functionality 1: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Core functionality 2: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Core functionality 3: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | ML model prediction: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Integration 1: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Integration 2: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Dashboard/reporting: Pass/Fail
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Overall smoke test: Pass/Fail (must be 100%)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Smoke test completion time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Post-Deployment Checks
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Application responding: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | All services running: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Database connections working: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Integrations functioning: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Monitoring collecting data: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Alerts functioning: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Logs being captured: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Performance within SLAs: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | User Acceptance in Production
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Key users validated production system: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Business critical processes validated: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | User feedback collected
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Any immediate issues identified: _____ (resolved: Yes/No)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Users ready to proceed: Yes/No
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Post-deployment validation successful
WEEK 4: DEPLOYMENT & GO-LIVE | 4.3 Post-Deployment Validation | Smoke test results (100% pass)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Go-Live Announcement
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Go-live confirmed: Time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Go-live announcement sent to:
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | All users
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Executive sponsors
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | IT organization
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Business stakeholders
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | External partners (if applicable)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Announcement includes:
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | System is live and available
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | How to access
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Key features
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Where to get help
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Support contact information
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Hypercare Activation
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Hypercare period: _____ days (typically 30 days)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Hypercare team assembled:
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Hypercare Lead: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Business SME: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Technical Lead: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Developer (on-call): ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Support Lead: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Hypercare schedule:
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Week 1: 24/7 coverage
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Week 2-4: Extended hours coverage
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | War room schedule: Daily for first week
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Escalation procedures active
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Daily status meetings scheduled: Time: ___________
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Monitoring & Alerting Active
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | All monitoring dashboards active
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Alert rules operational
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | On-call rotations active
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Incident response procedures active
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Issues being tracked in real-time
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Early Issue Management
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Issue tracking system active
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Issues logged: _____ (first 24 hours)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Critical issues: _____ (resolved: _____)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | High issues: _____ (resolved: _____)
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Issue resolution tracking
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | User communication for known issues
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Go-live announcement sent
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Hypercare activated
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Monitoring operational
WEEK 4: DEPLOYMENT & GO-LIVE | 4.4 Go-Live Announcement & Hypercare Activation | Issue tracking active
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | 24/7 Support Coverage
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Support coverage: 24/7
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | On-call rotation active
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | War room operational
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Rapid response to critical issues
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Daily Status Meetings
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Day 1 meeting: Date: ___________ Issues: _____ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Day 2 meeting: Date: ___________ Issues: _____ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Day 3 meeting: Date: ___________ Issues: _____ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Day 4 meeting: Date: ___________ Issues: _____ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Day 5 meeting: Date: ___________ Issues: _____ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Day 6 meeting: Date: ___________ Issues: _____ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Day 7 meeting: Date: ___________ Issues: _____ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Week 1 Metrics
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | System uptime: _____% (Target: >99%)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Total incidents: _____
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Critical incidents: _____ (Target: 0)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Average incident response time: _____ minutes (Target: <30 min)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Average incident resolution time: _____ hours (Target: <4 hours)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | User adoption: _____% of expected users
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | User satisfaction: _____/5 (Target: >4.0)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Support tickets: _____
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Model performance: _____% accuracy (vs. baseline: _____%)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Week 1 Actions
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Critical issues resolved: _____ of _____
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Hot fixes deployed: _____
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Documentation updates: _____
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Training refreshers: _____ sessions
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Known issues communicated to users
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Week 1 status report
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Week 1 (Days 1-7) | Week 1 metrics dashboard
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Extended Hours Support
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Support coverage hours: _____ (e.g., 6am-10pm)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | On-call for after-hours
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Issue resolution ongoing
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Daily Monitoring (Weeks 2-3)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | System health monitored daily
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Performance metrics reviewed daily
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | User adoption tracked daily
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Issues triaged and resolved
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Weekly Status Meetings (Weeks 2-4)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Week 2 meeting: Date: ___________ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Week 3 meeting: Date: ___________ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Week 4 meeting: Date: ___________ Status: ___________
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Hypercare Metrics (30-day summary)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Overall system uptime: _____% (Target: >99%)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Total incidents: _____
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Critical incidents: _____ (Target: 0)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Average resolution time: _____ hours (Target: <4 hours)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | User adoption: _____% (Target: >80%)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | User satisfaction: _____/5 (Target: >4.0)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Support tickets resolved: _____% (Target: >95%)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Model performance: Stable/Degraded (accuracy: _____%)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Continuous Improvement
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | User feedback analyzed
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Quick wins identified and implemented: _____
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Training gaps identified and addressed
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Documentation updated based on issues
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Process improvements implemented
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | Weekly status reports (weeks 2-4)
HYPERCARE PERIOD (DAYS 1-30 POST GO-LIVE) | Hypercare Weeks 2-4 (Days 8-30) | 30-day hypercare summary report
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Hypercare Review Meeting
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Meeting date: ___________
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Hypercare metrics reviewed
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Success criteria assessment:
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | System stability: >99% uptime ✓/✗
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | No critical incidents in week 4: ✓/✗
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | User adoption: >80% ✓/✗
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | User satisfaction: >4.0/5 ✓/✗
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Outstanding issues reviewed: _____
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Lessons learned captured
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Transition readiness assessed: Ready/Not Ready
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Transition to BAU (Business as Usual)
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Support transitioned to standard support team
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Support hours: _____ (business hours + on-call)
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Standard support SLAs active
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Escalation procedures updated
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Operations team fully trained: Yes/No
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Knowledge transfer completed: Yes/No
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Operations runbooks validated: Yes/No
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Hypercare Report
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Comprehensive hypercare report created:
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Executive summary
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Hypercare metrics summary
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Issues summary and resolution
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | User feedback summary
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Model performance summary
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Lessons learned
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Recommendations
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Report shared with stakeholders
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Report archived in project repository
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Project Closure Handoff
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Formal handoff to Operate & Care phase
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Project team transition plan
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Ongoing support and optimization plan
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Technical debt log handed over
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Feature backlog handed over to product team
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Phase gate sign-off: ___________ Date: ___________
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Hypercare summary report
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Transition to BAU completed
HYPERCARE CLOSURE & TRANSITION | Hypercare End Activities | Handoff to Operate & Care phase
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Deployment Success
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Application successfully deployed to production
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Post-deployment smoke tests passed (100%)
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | All critical functionality working in production
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | No P1/P2 defects in production
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Training Completed
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | User training completion: >90%
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Administrator training completion: 100%
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Support team training completion: 100%
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Training evaluation scores: >4.0/5
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Operational Readiness
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Support infrastructure operational (helpdesk, ticketing)
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Monitoring and alerting active
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Backups configured and validated
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Disaster recovery plan validated
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Operations runbooks validated
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Change Management
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Change management activities completed
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | User communication campaign executed
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Change readiness: Ready
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | User accounts provisioned (100%)
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Hypercare Success
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | 30-day hypercare period completed
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | System uptime: >99%
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | No critical incidents in final week
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | User adoption: >80%
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | User satisfaction: >4.0/5
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Business Value
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Business processes enabled
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Users actively using system
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Early benefits realized
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Business stakeholders satisfied
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Documentation
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | All deployment documentation complete
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | User documentation validated
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Operations documentation complete
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Hypercare report completed
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Governance
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Steering committee approval obtained
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Phase gate review completed
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Approval to transition to Operate & Care phase
PHASE GATE: PREPARE & DEPLOY COMPLETE |  | Project closure activities initiated