## Business Envisioning Workshop
Phase/Section | Subsection | Task/Item | Status | Owner | Due Date | Notes
4 WEEKS BEFORE WORKSHOP | Stakeholder Alignment | Executive sponsor identified and committed
4 WEEKS BEFORE WORKSHOP | Stakeholder Alignment | Workshop objectives aligned with sponsor
4 WEEKS BEFORE WORKSHOP | Stakeholder Alignment | Initial 1-on-1 meetings scheduled with key stakeholders (30 min each)
4 WEEKS BEFORE WORKSHOP | Stakeholder Alignment | Participant list drafted and reviewed
4 WEEKS BEFORE WORKSHOP | Initial Planning | Workshop format determined (full day vs. half-days, in-person vs. virtual)
4 WEEKS BEFORE WORKSHOP | Initial Planning | Primary and backup dates identified
4 WEEKS BEFORE WORKSHOP | Initial Planning | Co-facilitators identified (technical expert, scribe)
4 WEEKS BEFORE WORKSHOP | Initial Planning | Budget approved for workshop
3 WEEKS BEFORE WORKSHOP | Stakeholder Discovery | 1-on-1 pre-interviews completed with key stakeholders
3 WEEKS BEFORE WORKSHOP | Stakeholder Discovery | Pre-interview insights synthesized
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Workshop date finalized and confirmed with all participants
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Calendar invitations sent with:
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Venue booked (for in-person)
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Virtual meeting setup (for virtual)
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Digital collaboration tool selected and set up
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Miro board created and configured
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Mural board created and configured
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Microsoft Whiteboard created
3 WEEKS BEFORE WORKSHOP | Logistics Setup | Other: ___________
2 WEEKS BEFORE WORKSHOP | Content Preparation | Workshop agenda finalized
2 WEEKS BEFORE WORKSHOP | Content Preparation | Pre-read materials prepared
2 WEEKS BEFORE WORKSHOP | Content Preparation | Pre-work assignment created and customized
2 WEEKS BEFORE WORKSHOP | Content Preparation | Workshop templates prepared
2 WEEKS BEFORE WORKSHOP | Content Preparation | Presentation deck created
2 WEEKS BEFORE WORKSHOP | Content Preparation | Digital collaboration board set up
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Physical materials ordered (for in-person)
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Sticky notes (multiple colors) - 20 pads
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Markers (thick) - 20 count
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Flip chart paper - 50 sheets
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Tape/adhesive
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Printed agenda (one per participant)
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Printed templates (backup)
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Name tents/tags
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Pens/notebooks
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Catering arranged (for in-person)
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Coffee/tea for arrival
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Morning break snacks
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Lunch (dietary restrictions accommodated)
2 WEEKS BEFORE WORKSHOP | Materials and Supplies | Afternoon break snacks
2 WEEKS BEFORE WORKSHOP | Communication | Pre-read materials sent to participants (2 weeks before)
2 WEEKS BEFORE WORKSHOP | Communication | Pre-work assignment sent to participants (2 weeks before)
1 WEEK BEFORE WORKSHOP | Pre-Work Review | Pre-work submissions tracked
1 WEEK BEFORE WORKSHOP | Pre-Work Review | Submission rate: ____% (target: 80%)
1 WEEK BEFORE WORKSHOP | Pre-Work Review | Follow up with non-responders
1 WEEK BEFORE WORKSHOP | Pre-Work Review | Pre-work responses analyzed
1 WEEK BEFORE WORKSHOP | Pre-Work Review | Agenda refined based on pre-work insights
1 WEEK BEFORE WORKSHOP | Final Logistics | Participant confirmation complete
1 WEEK BEFORE WORKSHOP | Final Logistics | Confirmed attendance: ____%
1 WEEK BEFORE WORKSHOP | Final Logistics | Replacements identified for declines
1 WEEK BEFORE WORKSHOP | Final Logistics | Technology tested (for virtual)
1 WEEK BEFORE WORKSHOP | Final Logistics | Meeting link tested
1 WEEK BEFORE WORKSHOP | Final Logistics | Screen sharing tested
1 WEEK BEFORE WORKSHOP | Final Logistics | Breakout rooms tested
1 WEEK BEFORE WORKSHOP | Final Logistics | Miro/Mural access tested with sample users
1 WEEK BEFORE WORKSHOP | Final Logistics | Recording capability tested
1 WEEK BEFORE WORKSHOP | Final Logistics | Venue confirmed (for in-person)
1 WEEK BEFORE WORKSHOP | Final Logistics | Room setup confirmed (U-shape/rounds)
1 WEEK BEFORE WORKSHOP | Final Logistics | A/V equipment tested (projector, screens, microphones)
1 WEEK BEFORE WORKSHOP | Final Logistics | WiFi access tested
1 WEEK BEFORE WORKSHOP | Final Logistics | Backup room identified (if needed)
1 WEEK BEFORE WORKSHOP | Final Preparation | Facilitator prep session held
1 WEEK BEFORE WORKSHOP | Final Preparation | Detailed facilitation script reviewed
1 WEEK BEFORE WORKSHOP | Final Preparation | Participant prep email sent (5 days before)
2-3 DAYS BEFORE WORKSHOP | Final Touches | All pre-work submissions received and reviewed
2-3 DAYS BEFORE WORKSHOP | Final Touches | Presentation deck finalized
2-3 DAYS BEFORE WORKSHOP | Final Touches | Digital board finalized and tested
2-3 DAYS BEFORE WORKSHOP | Final Touches | Backup plans prepared
2-3 DAYS BEFORE WORKSHOP | Final Touches | Facilitator guide printed/accessible
DAY BEFORE WORKSHOP | Final Checks | Reminder sent to all participants
DAY BEFORE WORKSHOP | Final Checks | Room setup confirmed (for in-person)
DAY BEFORE WORKSHOP | Final Checks | Virtual setup tested again
DAY BEFORE WORKSHOP | Final Checks | Catering confirmed (for in-person)
DAY BEFORE WORKSHOP | Final Checks | Facilitator team final sync
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Arrive early and set up room
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Test all A/V equipment
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Materials staged
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Welcome area set up
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Log in 30 minutes early
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Test all functionality
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Welcome slide displayed
WORKSHOP DAY - PRE-SESSION | Setup (60-90 minutes before start) | Co-facilitators in room and ready
WORKSHOP DAY - PRE-SESSION | Final Prep (15 minutes before start) | Facilitator team huddle
WORKSHOP DAY - PRE-SESSION | Final Prep (15 minutes before start) | Welcome participants as they arrive
WORKSHOP DAY - DURING SESSION | Activity 1: Welcome & Introductions (30 min) | Start on time
WORKSHOP DAY - DURING SESSION | Activity 1: Welcome & Introductions (30 min) | Welcome and set tone
WORKSHOP DAY - DURING SESSION | Activity 1: Welcome & Introductions (30 min) | Introductions completed
WORKSHOP DAY - DURING SESSION | Activity 1: Welcome & Introductions (30 min) | Agenda reviewed
WORKSHOP DAY - DURING SESSION | Activity 1: Welcome & Introductions (30 min) | Ground rules established
WORKSHOP DAY - DURING SESSION | Activity 1: Welcome & Introductions (30 min) | Ice breaker conducted
WORKSHOP DAY - DURING SESSION | Activity 1: Welcome & Introductions (30 min) | Parking lot set up
WORKSHOP DAY - DURING SESSION | Activity 2: Strategic Context & Vision (60 min) | Executive sponsor shares strategic context
WORKSHOP DAY - DURING SESSION | Activity 2: Strategic Context & Vision (60 min) | AI art-of-the-possible presented
WORKSHOP DAY - DURING SESSION | Activity 2: Strategic Context & Vision (60 min) | Industry examples shared
WORKSHOP DAY - DURING SESSION | Activity 2: Strategic Context & Vision (60 min) | Vision statement co-created
WORKSHOP DAY - DURING SESSION | Activity 2: Strategic Context & Vision (60 min) | Vision validated and approved
WORKSHOP DAY - DURING SESSION | Activity 3: Business Problem Exploration (75 min) | Problem definition framework explained
WORKSHOP DAY - DURING SESSION | Activity 3: Business Problem Exploration (75 min) | Silent brainstorm completed
WORKSHOP DAY - DURING SESSION | Activity 3: Business Problem Exploration (75 min) | Gallery walk and clustering done
WORKSHOP DAY - DURING SESSION | Activity 3: Business Problem Exploration (75 min) | Top 3-5 problems selected
WORKSHOP DAY - DURING SESSION | Activity 3: Business Problem Exploration (75 min) | Five Whys root cause analysis completed for each problem
WORKSHOP DAY - DURING SESSION | Activity 3: Business Problem Exploration (75 min) | Deep dive discussions completed for each
WORKSHOP DAY - DURING SESSION | Activity 3: Business Problem Exploration (75 min) | Impact quantified
WORKSHOP DAY - DURING SESSION | Break (15 min) | Break taken on schedule
WORKSHOP DAY - DURING SESSION | Activity 4: AI Use Case Ideation (90 min) | AI capability primer delivered
WORKSHOP DAY - DURING SESSION | Activity 4: AI Use Case Ideation (90 min) | Structured ideation completed
WORKSHOP DAY - DURING SESSION | Activity 4: AI Use Case Ideation (90 min) | 10-15 use cases selected for development
WORKSHOP DAY - DURING SESSION | Activity 4: AI Use Case Ideation (90 min) | Small groups developed use cases
WORKSHOP DAY - DURING SESSION | Activity 4: AI Use Case Ideation (90 min) | Each use case validated against root causes from Five Whys
WORKSHOP DAY - DURING SESSION | Activity 4: AI Use Case Ideation (90 min) | Gallery walk and share completed
WORKSHOP DAY - DURING SESSION | Lunch Break (60 min) | Lunch on schedule
WORKSHOP DAY - DURING SESSION | Activity 5: Use Case Prioritization (60 min) | Prioritization framework explained
WORKSHOP DAY - DURING SESSION | Activity 5: Use Case Prioritization (60 min) | Individual scoring completed
WORKSHOP DAY - DURING SESSION | Activity 5: Use Case Prioritization (60 min) | Consensus scoring achieved
WORKSHOP DAY - DURING SESSION | Activity 5: Use Case Prioritization (60 min) | 2x2 matrix plotted
WORKSHOP DAY - DURING SESSION | Activity 5: Use Case Prioritization (60 min) | Roadmap sequenced
WORKSHOP DAY - DURING SESSION | Activity 6: Success Criteria & Value Definition (60 min) | Success metrics framework explained
WORKSHOP DAY - DURING SESSION | Activity 6: Success Criteria & Value Definition (60 min) | Success criteria defined for top use cases
WORKSHOP DAY - DURING SESSION | Activity 6: Success Criteria & Value Definition (60 min) | Value realization framework created
WORKSHOP DAY - DURING SESSION | Activity 6: Success Criteria & Value Definition (60 min) | Measurement plan established
WORKSHOP DAY - DURING SESSION | Activity 6: Success Criteria & Value Definition (60 min) | ROI projections developed (cost savings, revenue impact, efficiency gains)
WORKSHOP DAY - DURING SESSION | Activity 6: Success Criteria & Value Definition (60 min) | Financial scenarios created (best case, likely case, conservative case)
WORKSHOP DAY - DURING SESSION | Break (15 min) | Break taken on schedule
WORKSHOP DAY - DURING SESSION | Activity 6A: Executive Decision Points & Risk Governance (30 min) | Investment thresholds discussed
WORKSHOP DAY - DURING SESSION | Activity 6A: Executive Decision Points & Risk Governance (30 min) | Risk & governance framework addressed
WORKSHOP DAY - DURING SESSION | Activity 6A: Executive Decision Points & Risk Governance (30 min) | Change management implications discussed
WORKSHOP DAY - DURING SESSION | Activity 6A: Executive Decision Points & Risk Governance (30 min) | Strategic options evaluated
WORKSHOP DAY - DURING SESSION | Activity 7: Feasibility & Constraints (45 min) | Feasibility dimensions explained
WORKSHOP DAY - DURING SESSION | Activity 7: Feasibility & Constraints (45 min) | Constraints identified for each use case
WORKSHOP DAY - DURING SESSION | Activity 7: Feasibility & Constraints (45 min) | Risks documented
WORKSHOP DAY - DURING SESSION | Activity 7: Feasibility & Constraints (45 min) | Go/No-Go decisions made
WORKSHOP DAY - DURING SESSION | Activity 7: Feasibility & Constraints (45 min) | AI maturity assessment conducted
WORKSHOP DAY - DURING SESSION | Activity 7: Feasibility & Constraints (45 min) | Competitive positioning evaluated
WORKSHOP DAY - DURING SESSION | Activity 8: Roadmap & Next Steps (30 min) | Workshop synthesis presented
WORKSHOP DAY - DURING SESSION | Activity 8: Roadmap & Next Steps (30 min) | High-level roadmap reviewed
WORKSHOP DAY - DURING SESSION | Activity 8: Roadmap & Next Steps (30 min) | Immediate next steps defined
WORKSHOP DAY - DURING SESSION | Activity 8: Roadmap & Next Steps (30 min) | Action items assigned with owners and dates
WORKSHOP DAY - DURING SESSION | Activity 8: Roadmap & Next Steps (30 min) | Closing and appreciation
WORKSHOP DAY - DURING SESSION | Post-Workshop Immediate | Take photos of all flip charts/whiteboards (in-person)
WORKSHOP DAY - DURING SESSION | Post-Workshop Immediate | Save/export all digital collaboration boards
WORKSHOP DAY - DURING SESSION | Post-Workshop Immediate | Collect all sticky notes and artifacts
WORKSHOP DAY - DURING SESSION | Post-Workshop Immediate | Gather feedback (informal check-out)
WORKSHOP DAY - DURING SESSION | Post-Workshop Immediate | Facilitator team debrief (15 min)
POST-WORKSHOP - WITHIN 24 HOURS | Documentation | Upload all photos and digital artifacts to shared folder
POST-WORKSHOP - WITHIN 24 HOURS | Documentation | Transcribe key outputs
POST-WORKSHOP - WITHIN 24 HOURS | Documentation | Create action item tracker
POST-WORKSHOP - WITHIN 24 HOURS | Communication | Send thank you email to participants
POST-WORKSHOP - WITHIN 24 HOURS | Communication | Inform executive sponsor of outcomes
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | Comprehensive workshop summary report created
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | Executive decision memo created (1-2 pages)
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | Board presentation deck created (if applicable)
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | 90-day action plan created
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | Executive dashboard mockup created
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | Use case documents created for top 3-5 use cases
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | Initial roadmap document created
POST-WORKSHOP - WITHIN 3 DAYS | Deliverables | Presentation deck created for leadership
POST-WORKSHOP - WITHIN 3 DAYS | Distribution | Workshop summary distributed to all participants
POST-WORKSHOP - WITHIN 3 DAYS | Distribution | Request feedback via survey
POST-WORKSHOP - WITHIN 1 WEEK | Validation | Financial estimates validated with finance team
POST-WORKSHOP - WITHIN 1 WEEK | Validation | Technical feasibility confirmed with IT/architecture
POST-WORKSHOP - WITHIN 1 WEEK | Planning | Data assessment initiated
POST-WORKSHOP - WITHIN 1 WEEK | Planning | Project charter or business case drafted
POST-WORKSHOP - WITHIN 1 WEEK | Planning | Project governance structure defined
POST-WORKSHOP - WITHIN 1 WEEK | Planning | Team members identified for discovery phase
POST-WORKSHOP - WITHIN 2 WEEKS | Socialization | Executive leadership presentation delivered
POST-WORKSHOP - WITHIN 2 WEEKS | Socialization | Formal approval secured
POST-WORKSHOP - WITHIN 2 WEEKS | Socialization | Executive sponsor approval
POST-WORKSHOP - WITHIN 2 WEEKS | Socialization | Budget approval
POST-WORKSHOP - WITHIN 2 WEEKS | Socialization | Resource allocation approval
POST-WORKSHOP - WITHIN 2 WEEKS | Launch | Project initiation announced
POST-WORKSHOP - WITHIN 2 WEEKS | Launch | Discovery phase kickoff scheduled
POST-WORKSHOP - WITHIN 2 WEEKS | Launch | Quick win identified and initiated (if applicable)
POST-WORKSHOP - WITHIN 4 WEEKS | Transition | Discovery phase launched
POST-WORKSHOP - WITHIN 4 WEEKS | Transition | First steering committee meeting held
POST-WORKSHOP - WITHIN 4 WEEKS | Transition | Value tracking framework implemented
CONTINUOUS IMPROVEMENT | Lessons Learned | Helped uncover root causes effectively
CONTINUOUS IMPROVEMENT | Lessons Learned | Participants understood and engaged with the technique
CONTINUOUS IMPROVEMENT | Lessons Learned | Led to better-aligned AI solutions